## Sheet2
District | WorkOrderNum | DeviationName | CorrectionTime | Category | DeviationStatus | DateOfDeviation | SubCategory | Designation | IsPenalty | ServiceAffecting | Civil Foreman | Inspector | Expected Penalties
JEDDAH | 2521001669 | ALL REQUIRED WORKER UNIFORM AND SAFETY ITEMS ARE PRESENT? | 48 | Installation | Correction accepted by supervisor | 2026-03-11 02:22 | Safety | SAFETY | N | NO | Liyaqt | Mohamed Ali
JEDDAH | 2521001669 | HAVE ALL STC SAFETY MEASUREMENTS BEEN FOLLOWED? | 0 | Installation | Correction accepted by supervisor | 2026-03-11 02:22 | Safety | SAFETY | Y | NO | Liyaqt | Mohamed Ali
JEDDAH | 2521001669 | ALL HANDHOLES / MANHOLES ARE INSTALLED AS PER STC REQUIREMENTS? | 72 | Installation | Correction accepted by supervisor | 2026-03-11 02:47 | Hand hole/Manhole | CIVIL | Y | NO | Liyaqt | Mohamed Ali
JEDDAH | 2521001669 | IS THE TRENCH ROUTE STRAIGHT? | 72 | Trenching/bore | Correction accepted by supervisor | 2026-03-11 02:47 | CIVIL | CIVIL | N | NO | Liyaqt | Mohamed Ali
JEDDAH | 2521001669 | NUMBER OF SIGNBOARDS AVAILABLE IN THE SITE ARE SUFFICIENT? | 72 | Installation | Correction accepted by supervisor | 2026-03-11 02:47 | Safety | CIVIL | N | NO | Liyaqt | Mohamed Ali
JEDDAH | 2521001669 | IS THE TRENCH SEGMENT BACKFILLED WITH INSPECTOR APPROVAL? | 0 | Trenching/bore | Correction accepted by supervisor | 2026-03-15 13:02 | CIVIL | CIVIL | Y | NO | Liyaqt | Mohamed Ali
JEDDAH | 2521001669 | NO DEBRIS IS REMAINING ON THE SITE? | 48 | Installation | Correction accepted by supervisor | 2026-03-15 13:02 | CIVIL | CIVIL | Y | NO | Liyaqt | Mohamed Ali
JEDDAH | 2521001669 | ALL HANDHOLES / MANHOLES ARE INSTALLED AS PER STC REQUIREMENTS? | 72 | Installation | Correction accepted by supervisor | 2026-03-15 13:02 | Hand hole/Manhole | CIVIL | Y | NO | Liyaqt | Mohamed Ali
JEDDAH | 2521001669 | NUMBER OF SIGNBOARDS AVAILABLE IN THE SITE ARE SUFFICIENT? | 72 | Installation | Correction accepted by supervisor | 2026-03-16 00:29 | Safety | CIVIL | Y | NO | Liyaqt | Mohamed Ali
JEDDAH | 2521001669 | NO DEBRIS IS REMAINING ON THE SITE? | 48 | Installation | Correction accepted by supervisor | 2026-03-17 01:27 | CIVIL | CIVIL | Y | NO | Liyaqt | Mohamed Ali
JEDDAH | 2521001669 | IS THE TRENCH ROUTE STRAIGHT? | 72 | Trenching/bore | Correction accepted by supervisor | 2026-03-17 01:27 | CIVIL | CIVIL | Y | NO | Liyaqt | Mohamed Ali
JEDDAH | 2521001669 | THE TRENCH WIDTH IS AS PER DESIGN SPECIFICATIONS AND MEETS STC REQUIREMENTS? | 72 | Trenching/bore | Correction accepted by supervisor | 2026-03-17 01:27 | Standards | CIVIL | Y | NO | Liyaqt | Mohamed Ali
JEDDAH | 2521001669 | THE TRENCH DEPTH IS AS PER DESIGN SPECIFICATIONS AND MEETS STC REQUIREMENTS? | 72 | Trenching/bore | Correction accepted by supervisor | 2026-03-17 01:27 | Standards | CIVIL | Y | YES | Liyaqt | Mohamed Ali
JEDDAH | 2521001669 | THE CONDUITS ARE INSTALLED PER STC SPECIFICATIONS? | 72 | Installation | Correction accepted by supervisor | 2026-03-17 01:27 | Ducts | CIVIL | Y | NO | Liyaqt | Mohamed Ali
JEDDAH | 2521001669 | THE SPACERS ARE INSTALLED AS REQUIRED PER STC SPECIFICATIONS? | 72 | Installation | Correction accepted by supervisor | 2026-03-17 01:27 | Ducts | CIVIL | Y | NO | Liyaqt | Mohamed Ali
JEDDAH | 2521001669 | HAVE ALL STC SAFETY MEASUREMENTS BEEN FOLLOWED? | 0 | Installation | Correction accepted by supervisor | 2026-03-17 01:32 | Safety | SAFETY | Y | NO | Liyaqt | Mohamed Ali
JEDDAH | 2521001669 | PEDESTRIAN PASSES PLACED EVERY 100M IN FRONT OF CUSTOMER HOUSES AS REQUIRED | 0 | SAFETY | Correction accepted by supervisor | 2026-03-25 09:44 | INSTALLATION | SAFETY | Y | NO | Liyaqt | Mohamed Ali
JEDDAH | 2521001669 | HAVE ALL STC SAFETY MEASUREMENTS BEEN FOLLOWED? | 0 | Installation | Correction accepted by supervisor | 2026-03-25 09:44 | Safety | SAFETY | Y | NO | Liyaqt | Mohamed Ali
JEDDAH | 2521001669 | ALL REQUIRED WORKER UNIFORM AND SAFETY ITEMS ARE PRESENT? | 48 | Installation | Correction accepted by supervisor | 2026-03-25 09:45 | Safety | SAFETY | Y | NO | Liyaqt | Mohamed Ali
JEDDAH | 2521001669 | MUNCIPALITY PERMIT IS AVIALABLE ON THE SIGNBOARD? | 48 | Installation | Correction accepted by supervisor | 2026-03-25 09:45 | Safety | CIVIL | Y | NO | Liyaqt | Mohamed Ali
JEDDAH | 2521001669 | THE TRENCH DEPTH IS AS PER DESIGN SPECIFICATIONS AND MEETS STC REQUIREMENTS? | 72 | Trenching/bore | Correction accepted by supervisor | 2026-03-25 09:45 | Standards | CIVIL | Y | YES | Liyaqt | Mohamed Ali
JEDDAH | 2521001669 | MARKING TAPE PLACED AS PER STC SPECIFICATIONS (WARNING TAPE)? | 72 | Installation | Correction accepted by supervisor | 2026-03-25 09:45 | Standards | CIVIL | Y | YES | Liyaqt | Mohamed Ali
JEDDAH | 2521001669 | THE SPACERS ARE INSTALLED AS REQUIRED PER STC SPECIFICATIONS? | 72 | Installation | Correction accepted by supervisor | 2026-03-25 09:45 | Ducts | CIVIL | N | NO | Liyaqt | Mohamed Ali
JEDDAH | 2521001669 | DETECTABLE EMS PLACED AS PER STC SPECIFICATION? | 120 | Installation | Correction accepted by supervisor | 2026-03-25 09:45 | Standards | Fiber | Y | YES | Liyaqt | Mohamed Ali
JEDDAH | 2521001669 | WORKER NOT HOLDING STC ID BADGE | 0 | WORKER | Rejected deviation approved by supervisor | 2026-03-26 08:52 | WORKER REGISTERATION | CIVIL | N | NO | Liyaqt | Mohamed Ali | Yes
JEDDAH | 2521001669 | UNREGISTERED WORKER | 0 | WORKER | Rejected deviation approved by supervisor | 2026-03-26 08:52 | WORKER REGISTERATION | CIVIL | N | NO | Liyaqt | Mohamed Ali | Yes
JEDDAH | 2521001669 | NO DEBRIS IS REMAINING ON THE SITE? | 48 | Installation | Correction accepted by supervisor | 2026-03-26 09:31 | CIVIL | CIVIL | Y | NO | Liyaqt | Mohamed Ali
JEDDAH | 2521001669 | HAS THE TRENCH BEEN CLOSED WITHIN 24 HOURS OF OPENING? | 72 | Installation | Correction accepted by supervisor | 2026-03-26 09:31 | Safety | CIVIL | N | NO | Liyaqt | Mohamed Ali
JEDDAH | 2521001669 | HAVE ALL STC SAFETY MEASUREMENTS BEEN FOLLOWED? | 0 | Installation | Correction accepted by supervisor | 2026-03-26 09:34 | Safety | SAFETY | Y | NO | Liyaqt | Mohamed Ali
JEDDAH | 2521001669 | WORKER NOT HOLDING STC ID BADGE | 0 | WORKER | Closed by HQ | 2026-03-29 13:17 | WORKER REGISTERATION | CIVIL | N | NO | Liyaqt | Mohamed Ali | Yes
JEDDAH | 2521001669 | PEDESTRIAN PASSES PLACED EVERY 100M IN FRONT OF CUSTOMER HOUSES AS REQUIRED | 0 | SAFETY | Correction accepted by supervisor | 2026-03-29 13:30 | INSTALLATION | SAFETY | Y | NO | Liyaqt | Mohamed Ali
JEDDAH | 2521001669 | HAVE ALL STC SAFETY MEASUREMENTS BEEN FOLLOWED? | 0 | Installation | Correction accepted by supervisor | 2026-03-29 13:30 | Safety | SAFETY | Y | NO | Liyaqt | Mohamed Ali
JEDDAH | 2521001669 | THE CONDUITS ARE INSTALLED PER STC SPECIFICATIONS? | 72 | Installation | Correction accepted by supervisor | 2026-03-29 15:59 | Ducts | CIVIL | N | NO | Liyaqt | Mohamed Ali
JEDDAH | 2521001669 | NO DEBRIS IS REMAINING ON THE SITE? | 48 | Installation | Correction accepted by supervisor | 2026-04-05 12:44 | CIVIL | CIVIL | N | NO | Liyaqt | Mohamed Ali
JEDDAH | 2521001669 | THE SPACERS ARE INSTALLED AS REQUIRED PER STC SPECIFICATIONS? | 72 | Installation | Correction accepted by supervisor | 2026-04-05 12:44 | Ducts | CIVIL | N | NO | Liyaqt | Mohamed Ali
JEDDAH | 2521001669 | HAVE ALL STC SAFETY MEASUREMENTS BEEN FOLLOWED? | 0 | Installation | Correction accepted by supervisor | 2026-04-05 15:01 | Safety | SAFETY | Y | NO | Liyaqt | Mohamed Ali
JEDDAH | 2521001669 | WORKER NOT HOLDING STC ID BADGE | 0 | WORKER | Closed by HQ | 2026-04-06 12:06 | WORKER REGISTERATION | CIVIL | N | NO | Liyaqt | Mohamed Ali | Yes
JEDDAH | 2521001669 | ALL HANDHOLES / MANHOLES ARE INSTALLED AS PER STC REQUIREMENTS? | 72 | Installation | Correction accepted by supervisor | 2026-04-06 12:18 | Hand hole/Manhole | CIVIL | N | NO | Liyaqt | Mohamed Ali
JEDDAH | 2521001669 | HAVE ALL STC SAFETY MEASUREMENTS BEEN FOLLOWED? | 0 | Installation | Correction accepted by supervisor | 2026-04-06 12:20 | Safety | SAFETY | Y | NO | Liyaqt | Mohamed Ali
JEDDAH | 2521001669 | ALL REQUIRED WORKER UNIFORM AND SAFETY ITEMS ARE PRESENT? | 48 | Installation | Correction accepted by supervisor | 2026-04-06 12:22 | Safety | SAFETY | Y | NO | Liyaqt | Mohamed Ali
JEDDAH | 2521001669 | WORKER NOT HOLDING STC ID BADGE | 0 | WORKER | Closed by HQ | 2026-04-07 11:37 | WORKER REGISTERATION | CIVIL | N | NO | Liyaqt | Mohamed Ali | Yes
JEDDAH | 2521001669 | HAVE ALL STC SAFETY MEASUREMENTS BEEN FOLLOWED? | 0 | Installation | Correction accepted by supervisor | 2026-04-07 12:20 | Safety | SAFETY | Y | NO | Liyaqt | Mohamed Ali
JEDDAH | 2521001669 | MUNICIPALITY PERMITS ARE VALID AND RENEWED AS REQUIRED? | 0 | Trenching/bore | Rejected deviation approved by supervisor | 2026-04-07 12:22 | CIVIL | CIVIL | N | No | Liyaqt | Mohamed Ali
JEDDAH | 2521001669 | NO DEBRIS IS REMAINING ON THE SITE? | 48 | Installation | Correction accepted by supervisor | 2026-04-07 12:22 | CIVIL | CIVIL | N | NO | Liyaqt | Mohamed Ali
JEDDAH | 2521001669 | HAS THE TRENCH BEEN CLOSED WITHIN 24 HOURS OF OPENING? | 72 | Installation | Correction accepted by supervisor | 2026-04-07 12:22 | Safety | CIVIL | N | NO | Liyaqt | Mohamed Ali
JEDDAH | 2521001669 | THE BACKFILL MATERIALS SAND, CONCRETE, SUB BASE MEET SPECS/STANDARDS? | 72 | Material | Correction accepted by supervisor | 2026-04-07 12:22 | Standards | CIVIL | N | YES | Liyaqt | Mohamed Ali
JEDDAH | 2521001669 | MARKING TAPE PLACED AS PER STC SPECIFICATIONS (WARNING TAPE)? | 72 | Installation | Correction accepted by supervisor | 2026-04-07 12:23 | Standards | CIVIL | N | YES | Liyaqt | Mohamed Ali
JEDDAH | 2521001669 | THE CONDUITS ARE INSTALLED PER STC SPECIFICATIONS? | 72 | Installation | Correction accepted by supervisor | 2026-04-07 12:23 | Ducts | CIVIL | N | NO | Liyaqt | Mohamed Ali
JEDDAH | 2521001669 | HAVE ALL STC SAFETY MEASUREMENTS BEEN FOLLOWED? | 0 | Installation | Correction accepted by supervisor | 2026-04-09 17:24 | Safety | SAFETY | Y | NO | Liyaqt | Mohamed Ali
JEDDAH | 2521001669 | MUNICIPALITY PERMITS ARE VALID AND RENEWED AS REQUIRED? | 0 | Trenching/bore | Rejected deviation approved by supervisor | 2026-04-09 17:24 | CIVIL | CIVIL | N | No | Liyaqt | Mohamed Ali
JEDDAH | 2521001669 | NUMBER OF SIGNBOARDS AVAILABLE IN THE SITE ARE SUFFICIENT? | 72 | Installation | Correction accepted by supervisor | 2026-04-09 17:24 | Safety | CIVIL | Y | NO | Liyaqt | Mohamed Ali
JEDDAH | 2521001669 | PEDESTRIAN PASSES PLACED EVERY 100M IN FRONT OF CUSTOMER HOUSES AS REQUIRED | 0 | SAFETY | Correction accepted by supervisor | 2026-04-12 12:00 | INSTALLATION | SAFETY | Y | NO | Liyaqt | Mohamed Ali
JEDDAH | 2521001669 | WORKER NOT HOLDING STC ID BADGE | 0 | WORKER | Closed by HQ | 2026-04-13 12:41 | WORKER REGISTERATION | CIVIL | N | NO | Liyaqt | Mohamed Ali | Yes
JEDDAH | 2521001669 | HAVE ALL STC SAFETY MEASUREMENTS BEEN FOLLOWED? | 0 | Installation | Correction accepted by supervisor | 2026-04-13 14:15 | Safety | SAFETY | Y | NO | Liyaqt | Mohamed Ali
JEDDAH | 2521001669 | PEDESTRIAN PASSES PLACED EVERY 100M IN FRONT OF CUSTOMER HOUSES AS REQUIRED | 0 | SAFETY | Correction accepted by supervisor | 2026-04-15 13:10 | INSTALLATION | SAFETY | Y | NO | Liyaqt | Mohamed Ali
JEDDAH | 2521001669 | HAVE ALL STC SAFETY MEASUREMENTS BEEN FOLLOWED? | 0 | Installation | Correction accepted by supervisor | 2026-04-15 13:10 | Safety | SAFETY | Y | NO | Liyaqt | Mohamed Ali
JEDDAH | 2521001669 | MUNICIPALITY PERMITS ARE VALID AND RENEWED AS REQUIRED? | 0 | Trenching/bore | Correction accepted by supervisor | 2026-04-15 13:10 | CIVIL | CIVIL | Y | No | Liyaqt | Mohamed Ali
JEDDAH | 2521001669 | NO DEBRIS IS REMAINING ON THE SITE? | 48 | Installation | Correction accepted by supervisor | 2026-04-15 13:10 | CIVIL | CIVIL | N | NO | Liyaqt | Mohamed Ali
JEDDAH | 2521001669 | NO DEBRIS IS REMAINING ON THE SITE? | 48 | Installation | Correction accepted by supervisor | 2026-04-21 13:09 | CIVIL | CIVIL | N | NO | Liyaqt | Mohamed Ali
JEDDAH | 2521001669 | HAVE ALL STC SAFETY MEASUREMENTS BEEN FOLLOWED? | 0 | Installation | Correction accepted by supervisor | 2026-04-21 13:09 | Safety | SAFETY | Y | NO | Liyaqt | Mohamed Ali
JEDDAH | 2521001669 | IS THE TRENCH ROUTE STRAIGHT? | 72 | Trenching/bore | Correction accepted by supervisor | 2026-04-22 13:47 | CIVIL | CIVIL | N | NO | Liyaqt | Mohamed Ali
JEDDAH | 2521001669 | THE TRENCH DEPTH IS AS PER DESIGN SPECIFICATIONS AND MEETS STC REQUIREMENTS? | 72 | Trenching/bore | Correction accepted by supervisor | 2026-04-22 13:47 | Standards | CIVIL | Y | YES | Liyaqt | Mohamed Ali
JEDDAH | 2521001669 | HAVE ALL STC SAFETY MEASUREMENTS BEEN FOLLOWED? | 0 | Installation | Correction accepted by supervisor | 2026-04-22 13:51 | Safety | SAFETY | Y | NO | Liyaqt | Mohamed Ali
JEDDAH | 2521001669 | ALL HANDHOLES / MANHOLES ARE INSTALLED AS PER STC REQUIREMENTS? | 72 | Installation | Correction accepted by supervisor | 2026-04-27 08:39 | Hand hole/Manhole | CIVIL | N | NO | Liyaqt | Mohamed Ali
JEDDAH | 2521001669 | ALL DAMAGE TO PROPERTY (TILES, CURBS, WALLS, ASPHALT) HAS BEEN REPAIRED TO ORIGINAL STATE OR AS PER CUSTOMER REQUEST AT WORK COMPLETION ? | 72 | Installation | Correction accepted by supervisor | 2026-04-30 09:29 | CIVIL | CIVIL | N | NO | Liyaqt | Mohamed Ali
JEDDAH | 2521001669 | HAS REINSTATEMENT BEEN COMPLETED WITHIN 120 HOURS OF TRENCH COMPLETION (CONCRETE PLACEMENT)? | 120 | Installation | Correction accepted by supervisor | 2026-04-30 09:30 | CIVIL | CIVIL | Y | NO | Liyaqt | Mohamed Ali
JEDDAH | 2521001669 | ALL INSTALLED PROTECTIVE U-GUARDS MEET STC SPECIFICATIONS? | 72 | Installation | Correction accepted by supervisor | 2026-04-30 09:31 | Standards | Fiber | N | NO | Liyaqt | Mohamed Ali
JEDDAH | 2521001669 | ARE ALL TB / OSB / ODB HAVE BEEN PROPERLY INSTALLED? | 72 | Installation | Correction accepted by supervisor | 2026-04-30 09:31 | Cabinets | Fiber | N | YES | Liyaqt | Mohamed Ali
JEDDAH | 2521001669 | NO DEBRIS IS REMAINING ON THE SITE? | 48 | Installation | Correction accepted by supervisor | 2026-05-06 11:04 | CIVIL | CIVIL | Y | NO | Liyaqt | Mohamed Ali
JEDDAH | 2521001669 | ALL DAMAGE TO PROPERTY (TILES, CURBS, WALLS, ASPHALT) HAS BEEN REPAIRED TO ORIGINAL STATE OR AS PER CUSTOMER REQUEST AT WORK COMPLETION ? | 72 | Installation | Correction accepted by supervisor | 2026-05-06 11:04 | CIVIL | CIVIL | Y | NO | Liyaqt | Mohamed Ali
JEDDAH | 2521001669 | ALL HANDHOLES / MANHOLES ARE INSTALLED AS PER STC REQUIREMENTS? | 72 | Installation | Correction accepted by supervisor | 2026-05-06 11:04 | Hand hole/Manhole | CIVIL | Y | NO | Liyaqt | Mohamed Ali
JEDDAH | 2521001669 | THE INSIDES OF THE INSTALLED MANHOLES / HANDHOLES ARE CLEAN AND ORANGANIZED (EXISTING MANHOLES/HANDHOLES HAVE BEEN REPORTED TO OM)? | 72 | Installation | Correction accepted by supervisor | 2026-05-11 09:31 | Hand hole/Manhole | CIVIL | N | NO | Liyaqt | Mohamed Ali
JEDDAH | 2521001669 | ALL VACANT DUCTS HAVE A PULL STRING AND THE PROPER DUCT SEALANT HAS BEEN APPLIED? | 72 | Installation | Correction accepted by supervisor | 2026-05-11 09:31 | Ducts | CIVIL | N | NO | Liyaqt | Mohamed Ali
JEDDAH | 2521001669 | ARE THE CABLES ROUTED AND RACKED CORRECTLY IN EACH MANHOLE / HANDHOLE? | 72 | Installation | Correction accepted by supervisor | 2026-05-11 09:31 | Design Compliance | Fiber | N | NO | Liyaqt | Mohamed Ali
JEDDAH | 2521001669 | HAS REINSTATEMENT BEEN COMPLETED WITHIN 120 HOURS OF TRENCH COMPLETION (CONCRETE PLACEMENT)? | 120 | Installation | Correction accepted by supervisor | 2026-05-11 11:14 | CIVIL | CIVIL | N | NO | Liyaqt | Mohamed Ali
JEDDAH | 2521001669 | ARE THE CABLES ROUTED AND RACKED CORRECTLY IN EACH MANHOLE / HANDHOLE? | 72 | Installation | Correction accepted by supervisor | 2026-05-13 11:52 | Design Compliance | Fiber | Y | NO | Liyaqt | Mohamed Ali
JEDDAH | 2521001663 | UNCERTIFIED WORKER | 0 | WORKER | Closed by HQ | 2026-01-14 09:57 | WORKER REGISTERATION | CIVIL | N | NO | Yasser Abdelrahaman | Mohamed Ali | Yes
JEDDAH | 2521001663 | WORKER NOT HOLDING STC ID BADGE | 0 | WORKER | Closed by HQ | 2026-01-15 12:05 | WORKER REGISTERATION | CIVIL | N | NO | Yasser Abdelrahaman | Mohamed Ali | Yes
JEDDAH | 2521001663 | WORKER NOT HOLDING STC ID BADGE | 0 | WORKER | Closed by HQ | 2026-01-15 12:06 | WORKER REGISTERATION | CIVIL | N | NO | Yasser Abdelrahaman | Mohamed Ali | Yes
JEDDAH | 2521001663 | WORKER NOT HOLDING STC ID BADGE | 0 | WORKER | Closed by HQ | 2026-01-19 11:07 | WORKER REGISTERATION | CIVIL | N | NO | Yasser Abdelrahaman | Mohamed Ali | Yes
JEDDAH | 2521001663 | NO DEBRIS IS REMAINING ON THE SITE? | 48 | Installation | Correction accepted by supervisor | 2026-01-19 11:57 | CIVIL | CIVIL | N | NO | Yasser Abdelrahaman | Mohamed Ali
JEDDAH | 2521001663 | NO DEBRIS IS REMAINING ON THE SITE? | 48 | Installation | Correction accepted by supervisor | 2026-01-21 15:10 | CIVIL | CIVIL | Y | NO | Yasser Abdelrahaman | Mohamed Ali
JEDDAH | 2521001663 | THE TRENCH WIDTH IS AS PER DESIGN SPECIFICATIONS AND MEETS STC REQUIREMENTS? | 72 | Trenching/bore | Rejected deviation approved by Regional supervisor | 2026-01-21 15:10 | Standards | CIVIL | N | NO | Yasser Abdelrahaman | Mohamed Ali
JEDDAH | 2521001663 | HAVE ALL STC SAFETY MEASUREMENTS BEEN FOLLOWED? | 0 | Installation | Correction accepted by supervisor | 2026-01-22 10:48 | Safety | SAFETY | Y | NO | Yasser Abdelrahaman | Mohamed Ali
JEDDAH | 2521001663 | STAND ALONE POWER SOURCE | 0 | SAFETY | Correction accepted by supervisor | 2026-01-22 10:49 | INSTALLATION | SAFETY | Y | NO | Yasser Abdelrahaman | Mohamed Ali
JEDDAH | 2521001663 | IS THE TRENCH ROUTE STRAIGHT? | 72 | Trenching/bore | Correction accepted by supervisor | 2026-01-22 11:25 | CIVIL | CIVIL | N | NO | Yasser Abdelrahaman | Mohamed Ali
JEDDAH | 2521001663 | NO DEBRIS IS REMAINING ON THE SITE? | 48 | Installation | Rejected deviation approved by Regional supervisor | 2026-01-22 11:25 | CIVIL | CIVIL | N | NO | Yasser Abdelrahaman | Mohamed Ali
JEDDAH | 2521001663 | MUNICIPALITY PERMITS ARE VALID AND RENEWED AS REQUIRED? | 0 | Trenching/bore | Rejected deviation approved by supervisor | 2026-01-22 11:36 | CIVIL | CIVIL | N | No | Yasser Abdelrahaman | Mohamed Ali
JEDDAH | 2521001663 | UNCERTIFIED WORKER | 0 | WORKER | Closed by HQ | 2026-01-25 14:15 | WORKER REGISTERATION | CIVIL | N | NO | Yasser Abdelrahaman | Mohamed Ali | Yes
JEDDAH | 2521001663 | HAVE ALL STC SAFETY MEASUREMENTS BEEN FOLLOWED? | 0 | Installation | Correction accepted by supervisor | 2026-01-25 14:37 | Safety | SAFETY | Y | NO | Yasser Abdelrahaman | Mohamed Ali
JEDDAH | 2521001663 | WORKER NOT HOLDING STC ID BADGE | 0 | WORKER | Closed by HQ | 2026-01-27 11:19 | WORKER REGISTERATION | CIVIL | N | NO | Yasser Abdelrahaman | Mohamed Ali | Yes
JEDDAH | 2521001663 | NO DEBRIS IS REMAINING ON THE SITE? | 48 | Installation | Correction accepted by supervisor | 2026-01-27 11:43 | CIVIL | CIVIL | N | NO | Yasser Abdelrahaman | Mohamed Ali
JEDDAH | 2521001663 | NO DEBRIS IS REMAINING ON THE SITE? | 48 | Installation | Rejected deviation approved by supervisor | 2026-01-28 13:39 | CIVIL | CIVIL | N | NO | Yasser Abdelrahaman | Mohamed Ali
JEDDAH | 2521001663 | IS THE TRENCH ROUTE STRAIGHT? | 72 | Trenching/bore | Correction accepted by supervisor | 2026-01-28 13:39 | CIVIL | CIVIL | Y | NO | Yasser Abdelrahaman | Mohamed Ali
JEDDAH | 2521001663 | UNCERTIFIED WORKER | 0 | WORKER | Closed by HQ | 2026-01-29 12:16 | WORKER REGISTERATION | CIVIL | N | NO | Yasser Abdelrahaman | Mohamed Ali | Yes
JEDDAH | 2521001663 | NO DEBRIS IS REMAINING ON THE SITE? | 48 | Installation | Correction accepted by supervisor | 2026-01-29 12:30 | CIVIL | CIVIL | N | NO | Yasser Abdelrahaman | Mohamed Ali
JEDDAH | 2521001663 | UNCERTIFIED WORKER | 0 | WORKER | Closed by HQ | 2026-02-01 12:42 | WORKER REGISTERATION | CIVIL | N | NO | Yasser Abdelrahaman | Mohamed Ali | Yes
JEDDAH | 2521001663 | UNCERTIFIED WORKER | 0 | WORKER | Closed by HQ | 2026-02-01 12:42 | WORKER REGISTERATION | CIVIL | N | NO | Yasser Abdelrahaman | Mohamed Ali | Yes
JEDDAH | 2521001663 | WORKER NOT HOLDING STC ID BADGE | 0 | WORKER | Closed by HQ | 2026-02-02 11:49 | WORKER REGISTERATION | CIVIL | N | NO | Yasser Abdelrahaman | Mohamed Ali | Yes
JEDDAH | 2521001663 | UNCERTIFIED WORKER | 0 | WORKER | Closed by HQ | 2026-02-02 11:50 | WORKER REGISTERATION | CIVIL | N | NO | Yasser Abdelrahaman | Mohamed Ali | Yes
JEDDAH | 2521001663 | MUNICIPALITY PERMITS ARE VALID AND RENEWED AS REQUIRED? | 0 | Trenching/bore | Rejected deviation approved by supervisor | 2026-02-02 12:32 | CIVIL | CIVIL | N | No | Yasser Abdelrahaman | Mohamed Ali
JEDDAH | 2521001663 | MUNCIPALITY PERMIT IS AVIALABLE ON THE SIGNBOARD? | 48 | Installation | Rejected deviation approved by supervisor | 2026-02-02 12:32 | Safety | CIVIL | N | NO | Yasser Abdelrahaman | Mohamed Ali
JEDDAH | 2521001663 | MUNCIPALITY PERMIT IS AVIALABLE ON THE SIGNBOARD? | 48 | Installation | Rejected deviation approved by Regional supervisor | 2026-02-04 11:47 | Safety | CIVIL | N | NO | Yasser Abdelrahaman | Mohamed Ali
JEDDAH | 2521001663 | HAS THE TRENCH BEEN CLOSED WITHIN 24 HOURS OF OPENING? | 72 | Installation | Correction accepted by supervisor | 2026-02-04 12:08 | Safety | CIVIL | Y | NO | Yasser Abdelrahaman | Mohamed Ali
JEDDAH | 2521001663 | PEDESTRIAN PASSES PLACED EVERY 100M IN FRONT OF CUSTOMER HOUSES AS REQUIRED | 0 | SAFETY | Correction accepted by supervisor | 2026-02-08 11:35 | INSTALLATION | SAFETY | Y | NO | Yasser Abdelrahaman | Mohamed Ali
JEDDAH | 2521001663 | WORKER NOT HOLDING STC ID BADGE | 0 | WORKER | Closed by HQ | 2026-02-09 12:50 | WORKER REGISTERATION | CIVIL | N | NO | Yasser Abdelrahaman | Mohamed Ali | Yes
JEDDAH | 2521001663 | NO DEBRIS IS REMAINING ON THE SITE? | 48 | Installation | Correction accepted by supervisor | 2026-02-09 13:11 | CIVIL | CIVIL | N | NO | Yasser Abdelrahaman | Mohamed Ali
JEDDAH | 2521001663 | UNCERTIFIED WORKER | 0 | WORKER | Closed by HQ | 2026-02-10 11:42 | WORKER REGISTERATION | CIVIL | N | NO | Yasser Abdelrahaman | Mohamed Ali | Yes
JEDDAH | 2521001663 | THE INSTALLED HAND HOLE / MANHOLE INCLUDES ALL REQUIRED ACCESSORIES? | 72 | Material | Rejected deviation approved by supervisor | 2026-02-10 12:09 | Hand hole/Manhole | CIVIL | N | NO | Yasser Abdelrahaman | Mohamed Ali
JEDDAH | 2521001663 | THE INSIDES OF THE INSTALLED MANHOLES / HANDHOLES ARE CLEAN AND ORANGANIZED (EXISTING MANHOLES/HANDHOLES HAVE BEEN REPORTED TO OM)? | 72 | Installation | Rejected deviation approved by supervisor | 2026-02-10 12:09 | Hand hole/Manhole | CIVIL | N | NO | Yasser Abdelrahaman | Mohamed Ali
JEDDAH | 2521001663 | ALL CONDUITS HAVE BEEN SEALED PER STC STANDARDS BOTH INSIDE AND OUTSIDE OF THE MANHOLE / HANDHOLE? | 72 | Installation | Rejected deviation approved by supervisor | 2026-02-10 12:09 | Hand hole/Manhole | CIVIL | N | YES | Yasser Abdelrahaman | Mohamed Ali
JEDDAH | 2521001663 | UNCERTIFIED WORKER | 0 | WORKER | Closed by HQ | 2026-02-11 09:38 | WORKER REGISTERATION | CIVIL | N | NO | Yasser Abdelrahaman | Mohamed Ali | Yes
JEDDAH | 2521001663 | UNCERTIFIED WORKER | 0 | WORKER | Closed by HQ | 2026-02-12 09:26 | WORKER REGISTERATION | CIVIL | N | NO | Yasser Abdelrahaman | Mohamed Ali | Yes
JEDDAH | 2521001663 | NO DEBRIS IS REMAINING ON THE SITE? | 48 | Installation | Correction accepted by supervisor | 2026-02-15 12:23 | CIVIL | CIVIL | N | NO | Yasser Abdelrahaman | Mohamed Ali
JEDDAH | 2521001663 | PEDESTRIAN PASSES PLACED EVERY 100M IN FRONT OF CUSTOMER HOUSES AS REQUIRED | 0 | SAFETY | Correction accepted by supervisor | 2026-02-17 14:27 | INSTALLATION | SAFETY | Y | NO | Yasser Abdelrahaman | Mohamed Ali
JEDDAH | 2521001663 | HAS THE TRENCH BEEN CLOSED WITHIN 24 HOURS OF OPENING? | 72 | Installation | Correction accepted by supervisor | 2026-02-17 19:52 | Safety | CIVIL | Y | NO | Yasser Abdelrahaman | Mohamed Ali
JEDDAH | 2521001663 | UNCERTIFIED WORKER | 0 | WORKER | Closed by HQ | 2026-02-19 00:15 | WORKER REGISTERATION | CIVIL | N | NO | Yasser Abdelrahaman | Mohamed Ali | Yes
JEDDAH | 2521001663 | IS THE TRENCH ROUTE STRAIGHT? | 72 | Trenching/bore | Correction accepted by supervisor | 2026-02-19 00:54 | CIVIL | CIVIL | Y | NO | Yasser Abdelrahaman | Mohamed Ali
JEDDAH | 2521001663 | NO DEBRIS IS REMAINING ON THE SITE? | 48 | Installation | Correction accepted by supervisor | 2026-02-24 20:53 | CIVIL | CIVIL | Y | NO | Yasser Abdelrahaman | Mohamed Ali
JEDDAH | 2521001663 | HAS THE TRENCH BEEN CLOSED WITHIN 24 HOURS OF OPENING? | 72 | Installation | Correction accepted by supervisor | 2026-02-24 20:53 | Safety | CIVIL | N | NO | Yasser Abdelrahaman | Mohamed Ali
JEDDAH | 2521001663 | PEDESTRIAN PASSES PLACED EVERY 100M IN FRONT OF CUSTOMER HOUSES AS REQUIRED | 0 | SAFETY | Correction accepted by supervisor | 2026-02-24 20:59 | INSTALLATION | SAFETY | Y | NO | Yasser Abdelrahaman | Mohamed Ali
JEDDAH | 2521001663 | HAVE ALL STC SAFETY MEASUREMENTS BEEN FOLLOWED? | 0 | Installation | Correction accepted by supervisor | 2026-02-24 20:59 | Safety | SAFETY | Y | NO | Yasser Abdelrahaman | Mohamed Ali
JEDDAH | 2521001663 | UNCERTIFIED WORKER | 0 | WORKER | Closed by HQ | 2026-02-26 00:07 | WORKER REGISTERATION | CIVIL | N | NO | Yasser Abdelrahaman | Mohamed Ali | Yes
JEDDAH | 2521001663 | MUNCIPALITY PERMIT IS AVIALABLE ON THE SIGNBOARD? | 48 | Installation | Rejected deviation approved by supervisor | 2026-03-01 21:48 | Safety | CIVIL | N | NO | Yasser Abdelrahaman | Mohamed Ali
JEDDAH | 2521001663 | NO DEBRIS IS REMAINING ON THE SITE? | 48 | Installation | Correction accepted by supervisor | 2026-03-01 21:48 | CIVIL | CIVIL | N | NO | Yasser Abdelrahaman | Mohamed Ali
JEDDAH | 2521001663 | IS THE TRENCH SEGMENT BACKFILLED WITH INSPECTOR APPROVAL? | 0 | Trenching/bore | Correction accepted by supervisor | 2026-03-02 16:48 | CIVIL | CIVIL | Y | NO | Yasser Abdelrahaman | Mohamed Ali
JEDDAH | 2521001663 | NO DEBRIS IS REMAINING ON THE SITE? | 48 | Installation | Correction accepted by supervisor | 2026-03-02 16:48 | CIVIL | CIVIL | N | NO | Yasser Abdelrahaman | Mohamed Ali
JEDDAH | 2521001663 | MUNCIPALITY PERMIT IS AVIALABLE ON THE SIGNBOARD? | 48 | Installation | Correction accepted by supervisor | 2026-03-04 00:44 | Safety | CIVIL | Y | NO | Yasser Abdelrahaman | Mohamed Ali
JEDDAH | 2521001663 | NO DEBRIS IS REMAINING ON THE SITE? | 48 | Installation | Correction accepted by supervisor | 2026-03-04 00:44 | CIVIL | CIVIL | N | NO | Yasser Abdelrahaman | Mohamed Ali
JEDDAH | 2521001663 | PEDESTRIAN PASSES PLACED EVERY 100M IN FRONT OF CUSTOMER HOUSES AS REQUIRED | 0 | SAFETY | Correction accepted by supervisor | 2026-03-04 01:37 | INSTALLATION | SAFETY | Y | NO | Yasser Abdelrahaman | Mohamed Ali
JEDDAH | 2521001663 | HAVE ALL STC SAFETY MEASUREMENTS BEEN FOLLOWED? | 0 | Installation | Correction accepted by supervisor | 2026-03-04 01:37 | Safety | SAFETY | Y | NO | Yasser Abdelrahaman | Mohamed Ali
JEDDAH | 2521001663 | NO DEBRIS IS REMAINING ON THE SITE? | 48 | Installation | Correction accepted by supervisor | 2026-03-09 00:27 | CIVIL | CIVIL | Y | NO | Yasser Abdelrahaman | Mohamed Ali
JEDDAH | 2521001663 | HAS THE TRENCH BEEN CLOSED WITHIN 24 HOURS OF OPENING? | 72 | Installation | Correction accepted by supervisor | 2026-03-09 00:27 | Safety | CIVIL | Y | NO | Yasser Abdelrahaman | Mohamed Ali
JEDDAH | 2521001663 | IS THE TRENCH ROUTE STRAIGHT? | 72 | Trenching/bore | Correction accepted by supervisor | 2026-03-10 00:41 | CIVIL | CIVIL | Y | NO | Yasser Abdelrahaman | Mohamed Ali
JEDDAH | 2521001663 | PEDESTRIAN PASSES PLACED EVERY 100M IN FRONT OF CUSTOMER HOUSES AS REQUIRED | 0 | SAFETY | Correction accepted by supervisor | 2026-03-10 00:53 | INSTALLATION | SAFETY | Y | NO | Yasser Abdelrahaman | Mohamed Ali
JEDDAH | 2521001663 | MUNCIPALITY PERMIT IS AVIALABLE ON THE SIGNBOARD? | 48 | Installation | Correction accepted by supervisor | 2026-03-11 02:17 | Safety | CIVIL | Y | NO | Yasser Abdelrahaman | Mohamed Ali
JEDDAH | 2521001663 | NO DEBRIS IS REMAINING ON THE SITE? | 48 | Installation | Correction accepted by supervisor | 2026-03-11 02:17 | CIVIL | CIVIL | N | NO | Yasser Abdelrahaman | Mohamed Ali
JEDDAH | 2521001663 | NO DEBRIS IS REMAINING ON THE SITE? | 48 | Installation | Correction accepted by supervisor | 2026-03-12 02:23 | CIVIL | CIVIL | Y | NO | Yasser Abdelrahaman | Mohamed Ali
JEDDAH | 2521001663 | NO DEBRIS IS REMAINING ON THE SITE? | 48 | Installation | Correction accepted by supervisor | 2026-03-31 13:20 | CIVIL | CIVIL | N | NO | Yasser Abdelrahaman | Mohamed Ali
JEDDAH | 2521001663 | THE SPACERS ARE INSTALLED AS REQUIRED PER STC SPECIFICATIONS? | 72 | Installation | Correction accepted by supervisor | 2026-03-31 13:20 | Ducts | CIVIL | N | NO | Yasser Abdelrahaman | Mohamed Ali
JEDDAH | 2521001663 | HAVE ALL STC SAFETY MEASUREMENTS BEEN FOLLOWED? | 0 | Installation | Correction accepted by supervisor | 2026-03-31 13:24 | Safety | SAFETY | Y | NO | Yasser Abdelrahaman | Mohamed Ali
JEDDAH | 2521001663 | ALL INSTALLED PROTECTIVE U-GUARDS MEET STC SPECIFICATIONS? | 72 | Installation | Correction accepted by supervisor | 2026-04-23 13:04 | Standards | Fiber | Y | NO | Yasser Abdelrahaman | Mohamed Ali
JEDDAH | 2521001663 | ALL INSTALLED PROTECTIVE U-GUARDS MEET STC SPECIFICATIONS? | 72 | Installation | Correction accepted by supervisor | 2026-04-29 08:47 | Standards | Fiber | N | NO | Yasser Abdelrahaman | Mohamed Ali
JEDDAH | 2521001663 | HAS THE CABLE BEEN PLACED AS PER DESIGN AND AS PER STC SPECIFICATIONS? | 72 | Installation | Correction accepted by supervisor | 2026-05-03 08:57 | Standards | Fiber | N | NO | Yasser Abdelrahaman | Mohamed Ali
JEDDAH | 2521001663 | ALL INSTALLED PROTECTIVE U-GUARDS MEET STC SPECIFICATIONS? | 72 | Installation | Correction accepted by supervisor | 2026-05-06 08:50 | Standards | Fiber | Y | NO | Yasser Abdelrahaman | Mohamed Ali
JEDDAH | 2521001663 | THE INSIDES OF THE INSTALLED MANHOLES / HANDHOLES ARE CLEAN AND ORANGANIZED (EXISTING MANHOLES/HANDHOLES HAVE BEEN REPORTED TO OM)? | 72 | Installation | Correction accepted by supervisor | 2026-05-11 09:50 | Hand hole/Manhole | CIVIL | N | NO | Yasser Abdelrahaman | Mohamed Ali
JEDDAH | 2521001663 | ALL VACANT DUCTS HAVE A PULL STRING AND THE PROPER DUCT SEALANT HAS BEEN APPLIED? | 72 | Installation | Correction accepted by supervisor | 2026-05-11 09:50 | Ducts | CIVIL | N | NO | Yasser Abdelrahaman | Mohamed Ali
JEDDAH | 2521001663 | ALL INSTALLED PROTECTIVE U-GUARDS MEET STC SPECIFICATIONS? | 72 | Installation | Correction accepted by supervisor | 2026-05-11 10:02 | Standards | Fiber | N | NO | Yasser Abdelrahaman | Mohamed Ali
JEDDAH | 2521001663 | ARE ALL TB / OSB / ODB HAVE BEEN PROPERLY INSTALLED? | 72 | Installation | Correction accepted by supervisor | 2026-05-11 10:02 | Cabinets | Fiber | N | YES | Yasser Abdelrahaman | Mohamed Ali
JEDDAH | 2521001668 | NO DEBRIS IS REMAINING ON THE SITE? | 48 | Installation | Correction accepted by supervisor | 2026-04-05 10:40 | CIVIL | CIVIL | N | NO | Abu omar | Mohamed Ali
JEDDAH | 2521001668 | IS THE TRENCH ROUTE STRAIGHT? | 72 | Trenching/bore | Correction accepted by supervisor | 2026-04-05 10:40 | CIVIL | CIVIL | N | NO | Abu omar | Mohamed Ali
JEDDAH | 2521001668 | HAVE ALL STC SAFETY MEASUREMENTS BEEN FOLLOWED? | 0 | Installation | Correction accepted by supervisor | 2026-04-05 10:58 | Safety | SAFETY | Y | NO | Abu omar | Mohamed Ali
JEDDAH | 2521001668 | WORKER NOT HOLDING STC ID BADGE | 0 | WORKER | Closed by HQ | 2026-04-06 11:51 | WORKER REGISTERATION | CIVIL | N | NO | Abu omar | Mohamed Ali | Yes
JEDDAH | 2521001668 | THE BACKFILL MATERIALS SAND, CONCRETE, SUB BASE MEET SPECS/STANDARDS? | 72 | Material | Correction accepted by supervisor | 2026-04-08 09:16 | Standards | CIVIL | N | YES | Abu omar | Mohamed Ali
JEDDAH | 2521001668 | MUNICIPALITY PERMITS ARE VALID AND RENEWED AS REQUIRED? | 0 | Trenching/bore | Correction accepted by supervisor | 2026-04-12 10:59 | CIVIL | CIVIL | Y | No | Abu omar | Mohamed Ali
JEDDAH | 2521001668 | THE REINSTATEMENT HAS BEEN COMPLETED AND MEETS MUNICIPALITY CLOSING REQUIREMENTS? | 72 | Installation | Correction accepted by supervisor | 2026-04-12 10:59 | Standards | CIVIL | N | NO | Abu omar | Mohamed Ali
JEDDAH | 2521001668 | THE TRENCH DEPTH IS AS PER DESIGN SPECIFICATIONS AND MEETS STC REQUIREMENTS? | 72 | Trenching/bore | Correction accepted by supervisor | 2026-04-12 10:59 | Standards | CIVIL | N | YES | Abu omar | Mohamed Ali
JEDDAH | 2521001668 | MARKING TAPE PLACED AS PER STC SPECIFICATIONS (WARNING TAPE)? | 72 | Installation | Correction accepted by supervisor | 2026-04-12 10:59 | Standards | CIVIL | N | YES | Abu omar | Mohamed Ali
JEDDAH | 2521001668 | HAVE ALL STC SAFETY MEASUREMENTS BEEN FOLLOWED? | 0 | Installation | Correction accepted by supervisor | 2026-04-12 11:00 | Safety | SAFETY | Y | NO | Abu omar | Mohamed Ali
JEDDAH | 2521001668 | HAVE ALL STC SAFETY MEASUREMENTS BEEN FOLLOWED? | 0 | Installation | Correction accepted by supervisor | 2026-04-15 11:20 | Safety | SAFETY | Y | NO | Abu omar | Mohamed Ali
JEDDAH | 2521001668 | HAS THE CABLE DRUM BEEN PLACED VERTICALLY DURING PULLING? | 0 | Installation | Correction accepted by supervisor | 2026-04-15 11:21 | Standards | Fiber | Y | NO | Abu omar | Mohamed Ali
JEDDAH | 2521001668 | NO DEBRIS IS REMAINING ON THE SITE? | 48 | Installation | Correction accepted by supervisor | 2026-04-16 09:55 | CIVIL | CIVIL | N | NO | Abu omar | Mohamed Ali
JEDDAH | 2521001668 | HAVE ALL STC SAFETY MEASUREMENTS BEEN FOLLOWED? | 0 | Installation | Correction accepted by supervisor | 2026-04-16 10:13 | Safety | SAFETY | Y | NO | Abu omar | Mohamed Ali
JEDDAH | 2521001668 | THE BACKFILL MATERIALS SAND, CONCRETE, SUB BASE MEET SPECS/STANDARDS? | 72 | Material | Correction accepted by supervisor | 2026-04-29 14:13 | Standards | CIVIL | N | YES | Abu omar | Mohamed Ali
JEDDAH | 2521001668 | ALL HANDHOLES / MANHOLES ARE INSTALLED AS PER STC REQUIREMENTS? | 72 | Installation | Correction accepted by supervisor | 2026-04-29 14:13 | Hand hole/Manhole | CIVIL | N | NO | Abu omar | Mohamed Ali
JEDDAH | 2521001668 | ALL INSTALLED PROTECTIVE U-GUARDS MEET STC SPECIFICATIONS? | 72 | Installation | Correction accepted by supervisor | 2026-04-29 14:13 | Standards | Fiber | N | NO | Abu omar | Mohamed Ali
JEDDAH | 2521001668 | NO DEBRIS IS REMAINING ON THE SITE? | 48 | Installation | Correction accepted by supervisor | 2026-04-30 11:11 | CIVIL | CIVIL | N | NO | Abu omar | Mohamed Ali
JEDDAH | 2521001668 | WORK HAS BEEN CLEANED AND RETURNED TO ORIGINAL STATE ? | 72 | Trenching/bore | Correction accepted by supervisor | 2026-04-30 11:11 | Standards | CIVIL | Y | NO | Abu omar | Mohamed Ali
JEDDAH | 2521001668 | HAS REINSTATEMENT BEEN COMPLETED WITHIN 120 HOURS OF TRENCH COMPLETION (CONCRETE PLACEMENT)? | 120 | Installation | Correction accepted by supervisor | 2026-04-30 11:11 | CIVIL | CIVIL | N | NO | Abu omar | Mohamed Ali
JEDDAH | 2521001668 | THE INSIDES OF THE INSTALLED MANHOLES / HANDHOLES ARE CLEAN AND ORANGANIZED (EXISTING MANHOLES/HANDHOLES HAVE BEEN REPORTED TO OM)? | 72 | Installation | Correction accepted by supervisor | 2026-04-30 11:11 | Hand hole/Manhole | CIVIL | N | NO | Abu omar | Mohamed Ali
JEDDAH | 2521001668 | ALL HANDHOLES / MANHOLES ARE INSTALLED AS PER STC REQUIREMENTS? | 72 | Installation | Correction accepted by supervisor | 2026-04-30 11:11 | Hand hole/Manhole | CIVIL | N | NO | Abu omar | Mohamed Ali
JEDDAH | 2521001668 | ALL VACANT DUCTS HAVE A PULL STRING AND THE PROPER DUCT SEALANT HAS BEEN APPLIED? | 72 | Installation | Correction accepted by supervisor | 2026-04-30 11:11 | Ducts | CIVIL | Y | NO | Abu omar | Mohamed Ali
JEDDAH | 2521001668 | ALL EXCESS MATERIAL AND WORK SCRAP HAS BEEN REMOVED FROM WORK SITE? | 72 | Installation | Correction accepted by supervisor | 2026-04-30 11:45 | CABLE | Fiber | N | NO | Abu omar | Mohamed Ali
JEDDAH | 2521001668 | ALL INSTALLED PROTECTIVE U-GUARDS MEET STC SPECIFICATIONS? | 72 | Installation | Correction accepted by supervisor | 2026-04-30 11:45 | Standards | Fiber | N | NO | Abu omar | Mohamed Ali
JEDDAH | 2521001668 | ARE THE CABLES ROUTED AND RACKED CORRECTLY IN EACH MANHOLE / HANDHOLE? | 72 | Installation | Correction accepted by supervisor | 2026-04-30 11:45 | Design Compliance | Fiber | Y | NO | Abu omar | Mohamed Ali
JEDDAH | 2521001668 | ARE ALL TB / OSB / ODB HAVE BEEN PROPERLY INSTALLED? | 72 | Installation | Correction accepted by supervisor | 2026-04-30 11:45 | Cabinets | Fiber | N | YES | Abu omar | Mohamed Ali
JEDDAH | 2521001668 | HAS REINSTATEMENT BEEN COMPLETED WITHIN 120 HOURS OF TRENCH COMPLETION (CONCRETE PLACEMENT)? | 120 | Installation | Correction accepted by supervisor | 2026-05-03 10:05 | CIVIL | CIVIL | N | NO | Abu omar | Mohamed Ali
JEDDAH | 2521001668 | ALL HANDHOLES / MANHOLES ARE INSTALLED AS PER STC REQUIREMENTS? | 72 | Installation | Rejected deviation approved by supervisor | 2026-05-03 10:05 | Hand hole/Manhole | CIVIL | N | NO | Abu omar | Mohamed Ali
JEDDAH | 2521001668 | ALL FIBERS ARE SPLICED IN CABINETS AND TERMINALS AS PER STC GUIDELINES? | 72 | Splicing | Correction accepted by supervisor | 2026-05-03 11:30 | Standards | Fiber | N | YES | Abu omar | Mohamed Ali
JEDDAH | 2521001668 | HAS THE CABLE BEEN PLACED AS PER DESIGN AND AS PER STC SPECIFICATIONS? | 72 | Installation | Correction accepted by supervisor | 2026-05-03 11:30 | Standards | Fiber | Y | NO | Abu omar | Mohamed Ali
JEDDAH | 2521001668 | ARE ALL TERMINALS (TB, OSB, ODB), CABINETS LABELED WITH PROPER IDENTIFICATION AND INFORMATION ? | 72 | Installation | Correction accepted by supervisor | 2026-05-07 12:57 | Labeling | Fiber | Y | NO | Abu omar | Mohamed Ali
JEDDAH | 2521001668 | NO DEBRIS IS REMAINING ON THE SITE? | 48 | Installation | Correction accepted by supervisor | 2026-05-10 08:15 | CIVIL | CIVIL | N | NO | Abu omar | Mohamed Ali
JEDDAH | 2521001662 | THE TRENCH DEPTH IS AS PER DESIGN SPECIFICATIONS AND MEETS STC REQUIREMENTS? | 72 | Trenching/bore | Correction accepted by supervisor | 2025-12-10 14:04 | Standards | CIVIL | N | YES | Tariq / Ammar | Islam Abdelkawi
JEDDAH | 2521001662 | THE TRENCH DEPTH IS AS PER DESIGN SPECIFICATIONS AND MEETS STC REQUIREMENTS? | 72 | Trenching/bore | Correction accepted by supervisor | 2025-12-28 13:40 | Standards | CIVIL | N | YES | Tariq / Ammar | Islam Abdelkawi
JEDDAH | 2521001662 | UNCERTIFIED WORKER | 0 | WORKER | Closed by HQ | 2026-01-01 11:03 | WORKER REGISTERATION | CIVIL | N | NO | Tariq / Ammar | Islam Abdelkawi | Yes
JEDDAH | 2521001662 | UNCERTIFIED WORKER | 0 | WORKER | Closed by HQ | 2026-01-01 11:03 | WORKER REGISTERATION | CIVIL | N | NO | Tariq / Ammar | Islam Abdelkawi | Yes
JEDDAH | 2521001662 | MUNICIPALITY PERMITS ARE VALID AND RENEWED AS REQUIRED? | 0 | Trenching/bore | Closed Deviation With Penalty Approved by HQPM | 2026-01-07 13:20 | CIVIL | CIVIL | N | No | Tariq / Ammar | Islam Abdelkawi | Yes
JEDDAH | 2521001662 | THE TRENCH DEPTH IS AS PER DESIGN SPECIFICATIONS AND MEETS STC REQUIREMENTS? | 72 | Trenching/bore | Correction accepted by supervisor | 2026-01-07 13:20 | Standards | CIVIL | N | YES | Tariq / Ammar | Islam Abdelkawi
JEDDAH | 2521001662 | THE BACKFILL MATERIALS SAND, CONCRETE, SUB BASE MEET SPECS/STANDARDS? | 72 | Material | Correction accepted by supervisor | 2026-01-07 13:20 | Standards | CIVIL | Y | YES | Tariq / Ammar | Islam Abdelkawi
JEDDAH | 2521001662 | NO DEBRIS IS REMAINING ON THE SITE? | 48 | Installation | Correction accepted by supervisor | 2026-01-19 14:40 | CIVIL | CIVIL | N | NO | Tariq / Ammar | Islam Abdelkawi
JEDDAH | 2521001662 | ALL DAMAGE TO PROPERTY (TILES, CURBS, WALLS, ASPHALT) HAS BEEN REPAIRED TO ORIGINAL STATE OR AS PER CUSTOMER REQUEST AT WORK COMPLETION ? | 72 | Installation | Correction accepted by supervisor | 2026-01-19 14:41 | CIVIL | CIVIL | N | NO | Tariq / Ammar | Islam Abdelkawi
JEDDAH | 2521001662 | ALL INSTALLED PROTECTIVE U-GUARDS MEET STC SPECIFICATIONS? | 72 | Installation | Correction accepted by supervisor | 2026-02-11 14:24 | Standards | Fiber | N | NO | Tariq / Ammar | Islam Abdelkawi
JEDDAH | 2521001662 | HAS THE CABLE BEEN PLACED AS PER DESIGN AND AS PER STC SPECIFICATIONS? | 72 | Installation | Correction accepted by supervisor | 2026-02-11 14:24 | Standards | Fiber | N | NO | Tariq / Ammar | Islam Abdelkawi
JEDDAH | 2521001662 | NO DEBRIS IS REMAINING ON THE SITE? | 48 | Installation | Correction accepted by supervisor | 2026-02-11 14:25 | CIVIL | CIVIL | N | NO | Tariq / Ammar | Islam Abdelkawi
JEDDAH | 2521001662 | WORK HAS BEEN CLEANED AND RETURNED TO ORIGINAL STATE ? | 72 | Trenching/bore | Correction accepted by supervisor | 2026-02-11 14:25 | Standards | CIVIL | Y | NO | Tariq / Ammar | Islam Abdelkawi
JEDDAH | 2521001662 | ALL DAMAGE TO PROPERTY (TILES, CURBS, WALLS, ASPHALT) HAS BEEN REPAIRED TO ORIGINAL STATE OR AS PER CUSTOMER REQUEST AT WORK COMPLETION ? | 72 | Installation | Correction accepted by supervisor | 2026-03-05 20:06 | CIVIL | CIVIL | Y | NO | Tariq / Ammar | Islam Abdelkawi
JEDDAH | 2521001662 | ALL DUCTS HAVE BEEN INSPECTED AND ARE FREE OF DAMAGE AND DEFECTS AND INCLUDE PROPER LABELING? | 0 | Material | Correction accepted by supervisor | 2026-03-22 07:28 | Ducts | CIVIL | Y | NO | Tariq / Ammar | Islam Abdelkawi
JEDDAH | 2521001662 | THE CONDUITS ARE INSTALLED PER STC SPECIFICATIONS? | 72 | Installation | Correction accepted by supervisor | 2026-03-22 07:28 | Ducts | CIVIL | Y | NO | Tariq / Ammar | Islam Abdelkawi
JEDDAH | 2521001662 | THE SPACERS ARE INSTALLED AS REQUIRED PER STC SPECIFICATIONS? | 72 | Installation | Correction accepted by supervisor | 2026-03-22 07:28 | Ducts | CIVIL | Y | NO | Tariq / Ammar | Islam Abdelkawi
JEDDAH | 2521001662 | ALL EXCESS MATERIAL AND WORK SCRAP HAS BEEN REMOVED FROM WORK SITE? | 72 | Installation | Correction accepted by supervisor | 2026-04-07 08:57 | CABLE | Fiber | N | NO | Tariq / Ammar | Islam Abdelkawi
JEDDAH | 2521001662 | ALL HANDHOLES / MANHOLES ARE INSTALLED AS PER STC REQUIREMENTS? | 72 | Installation | Correction accepted by supervisor | 2026-04-07 09:24 | Hand hole/Manhole | CIVIL | Y | NO | Tariq / Ammar | Islam Abdelkawi
JEDDAH | 2521001661 | ALL REQUIRED WORKER UNIFORM AND SAFETY ITEMS ARE PRESENT? | 48 | Installation | Correction accepted by supervisor | 2025-12-16 10:51 | Safety | SAFETY | N | NO | Adel
JEDDAH | 2521001661 | MUNICIPALITY PERMITS ARE VALID AND RENEWED AS REQUIRED? | 0 | Trenching/bore | Closed Deviation With Penalty Approved by HQPM | 2025-12-24 11:27 | CIVIL | CIVIL | N | No | Adel |  | Yes
JEDDAH | 2521001661 | MUNICIPALITY PERMITS ARE VALID AND RENEWED AS REQUIRED? | 0 | Trenching/bore | Rejected deviation approved by supervisor | 2025-12-29 13:38 | CIVIL | CIVIL | N | No | Adel
JEDDAH | 2521001661 | THE BACKFILL MATERIALS SAND, CONCRETE, SUB BASE MEET SPECS/STANDARDS? | 72 | Material | Correction accepted by supervisor | 2025-12-29 13:49 | Standards | CIVIL | N | YES | Adel
JEDDAH | 2521001661 | THE ASPHALT / CONCRETE WAS PROVIDED BY STC APPROVED SUPPLIER? | 72 | Material | Correction accepted by supervisor | 2025-12-29 14:00 | Type Approval | CIVIL | N | NO | Adel
JEDDAH | 2521001661 | NO DEBRIS IS REMAINING ON THE SITE? | 48 | Installation | Correction accepted by supervisor | 2026-01-13 14:20 | CIVIL | CIVIL | Y | NO | Adel
JEDDAH | 2521001661 | ALL INSTALLED PROTECTIVE U-GUARDS MEET STC SPECIFICATIONS? | 72 | Installation | Correction accepted by supervisor | 2026-01-13 14:23 | Standards | Fiber | N | NO | Adel
JEDDAH | 2521001661 | ALL DAMAGE TO PROPERTY (TILES, CURBS, WALLS, ASPHALT) HAS BEEN REPAIRED TO ORIGINAL STATE OR AS PER CUSTOMER REQUEST AT WORK COMPLETION ? | 72 | Installation | Correction accepted by supervisor | 2026-01-18 14:38 | CIVIL | CIVIL | N | NO | Adel
JEDDAH | 2521001661 | ALL MATERIALS PLACED AS CALLED FOR BY APPROVED DESIGN AND APPROVED STC SPECIFICATIONS? | 72 | Material | Correction accepted by supervisor | 2026-01-21 11:44 | Design Compliance | Fiber | N | NO | Adel
JEDDAH | 2521001661 | HAS THE CABLE BEEN PLACED AS PER DESIGN AND AS PER STC SPECIFICATIONS? | 72 | Installation | Correction accepted by supervisor | 2026-01-21 11:45 | Standards | Fiber | N | NO | Adel
JEDDAH | 2521001661 | HAS THE CABLE DRUM BEEN PLACED VERTICALLY DURING PULLING? | 0 | Installation | Correction accepted by supervisor | 2026-01-21 11:45 | Standards | Fiber | Y | NO | Adel
JEDDAH | 2521001661 | ONLY PROPER FIBER OPTIC TOOLS ARE USED DURING INSTALLATION? | 0 | Installation | Correction accepted by supervisor | 2026-01-21 11:45 | Standards | Fiber | Y | NO | Adel
JEDDAH | 2521001661 | ARE THE CABLES ROUTED AND RACKED CORRECTLY IN EACH MANHOLE / HANDHOLE? | 72 | Installation | Correction accepted by supervisor | 2026-01-21 11:45 | Design Compliance | Fiber | N | NO | Adel
JEDDAH | 2521001661 | SIGNBOAD AS PER STC SPECIFICATION (DEMINSIONS, CLARITY, …ETC)? | 0 | Installation | Correction accepted by supervisor | 2026-01-21 11:51 | Safety | SAFETY | Y | NO | Adel
JEDDAH | 2521001661 | HAVE ALL STC SAFETY MEASUREMENTS BEEN FOLLOWED? | 0 | Installation | Correction accepted by supervisor | 2026-01-21 11:51 | Safety | SAFETY | Y | NO | Adel
JEDDAH | 2521001661 | ALL REQUIRED WORKER UNIFORM AND SAFETY ITEMS ARE PRESENT? | 48 | Installation | Correction accepted by supervisor | 2026-01-21 11:51 | Safety | SAFETY | N | NO | Adel
RIYADH | 2512000177 | WORKER NOT HOLDING STC ID BADGE | 0 | WORKER | Closed by HQ | 2025-11-06 10:56 | WORKER REGISTERATION | CIVIL | N | NO | N/A | N/A | Yes
RIYADH | 2512000177 | UNREGISTERED WORKER | 0 | WORKER | Closed by HQ | 2025-11-06 10:56 | WORKER REGISTERATION | CIVIL | N | NO | N/A | N/A | Yes
RIYADH | 2512000177 | WORKER NOT HOLDING STC ID BADGE | 0 | WORKER | Closed by HQ | 2025-11-06 10:57 | WORKER REGISTERATION | CIVIL | N | NO | N/A | N/A | Yes
RIYADH | 2512000177 | UNREGISTERED WORKER | 0 | WORKER | Closed by HQ | 2025-11-06 10:57 | WORKER REGISTERATION | CIVIL | N | NO | N/A | N/A | Yes
RIYADH | 2512000177 | PEDESTRIAN PASSES PLACED EVERY 100M IN FRONT OF CUSTOMER HOUSES AS REQUIRED | 0 | SAFETY | Correction accepted by supervisor | 2025-11-06 11:00 | INSTALLATION | SAFETY | Y | NO | N/A | N/A
RIYADH | 2512000177 | STAND ALONE POWER SOURCE | 0 | SAFETY | Correction accepted by supervisor | 2025-11-06 11:00 | INSTALLATION | SAFETY | Y | NO | N/A | N/A
RIYADH | 2512000177 | SIGNBOAD AS PER STC SPECIFICATION (DEMINSIONS, CLARITY, …ETC)? | 0 | Installation | Correction accepted by supervisor | 2025-11-06 11:01 | Safety | SAFETY | Y | NO | N/A | N/A
RIYADH | 2512000177 | HAVE ALL STC SAFETY MEASUREMENTS BEEN FOLLOWED? | 0 | Installation | Correction accepted by supervisor | 2025-11-06 11:01 | Safety | SAFETY | Y | NO | N/A | N/A
RIYADH | 2512000177 | ALL REQUIRED WORKER UNIFORM AND SAFETY ITEMS ARE PRESENT? | 48 | Installation | Correction accepted by supervisor | 2025-11-06 11:01 | Safety | SAFETY | Y | NO | N/A | N/A
RIYADH | 2512000177 | MUNCIPALITY PERMIT IS AVIALABLE ON THE SIGNBOARD? | 48 | Installation | Correction accepted by supervisor | 2025-11-06 11:39 | Safety | CIVIL | Y | NO | N/A | N/A
RIYADH | 2512000177 | NUMBER OF SIGNBOARDS AVAILABLE IN THE SITE ARE SUFFICIENT? | 72 | Installation | Correction accepted by supervisor | 2025-11-06 11:39 | Safety | CIVIL | Y | NO | N/A | N/A
RIYADH | 2512000177 | CONTRACTOR’S SIGNBOARD COMPLIED WITH THE PROJECT AND CONTRACTOR NAME ? | 48 | Installation | Correction accepted by supervisor | 2025-11-06 11:40 | Safety | CIVIL | Y | NO | N/A | N/A
RIYADH | 2512000177 | CONTRACTOR DETAILS AVAILBLE ON THE SIGNBOARD (NAME, PHONE NUMBER, … ETC) | 48 | Installation | Correction accepted by supervisor | 2025-11-06 11:40 | Safety | CIVIL | Y | NO | N/A | N/A
RIYADH | 2512000177 | ALL DAMAGE TO PROPERTY (TILES, CURBS, WALLS, ASPHALT) HAS BEEN REPAIRED TO ORIGINAL STATE OR AS PER CUSTOMER REQUEST AT WORK COMPLETION ? | 72 | Installation | Correction accepted by supervisor | 2025-11-06 11:40 | CIVIL | CIVIL | Y | NO | N/A | N/A
RIYADH | 2512000177 | ALL MATERIALS INSTALLED ARE FROM APPROVED SUPPLIER AND HAVE A VALID STC TYPE APPROVAL? | 0 | Material | Rejected deviation approved by supervisor | 2025-11-06 11:40 | Type Approval | CIVIL | N | YES | N/A | N/A
RIYADH | 2512000177 | Is the H&S plan available, stamped and signed by contractor/ subcontractor? | 0 | Pre-survey | Correction accepted by supervisor | 2025-11-06 11:53 | Pre-survey | CIVIL | Y | NO | N/A | N/A
RIYADH | 2512000177 | Unregistered Subcontractor | 0 | SubContractor | Closed by HQ | 2025-11-10 10:46 | SubContractor REGISTERATION | CIVIL | N | NO | N/A | N/A | Yes
RIYADH | 2512000177 | WORKER NOT HOLDING STC ID BADGE | 0 | WORKER | Closed by HQ | 2025-11-10 10:54 | WORKER REGISTERATION | CIVIL | N | NO | N/A | N/A | Yes
RIYADH | 2512000177 | UNREGISTERED WORKER | 0 | WORKER | Closed by HQ | 2025-11-10 10:54 | WORKER REGISTERATION | CIVIL | N | NO | N/A | N/A | Yes
RIYADH | 2512000177 | PEDESTRIAN PASSES PLACED EVERY 100M IN FRONT OF CUSTOMER HOUSES AS REQUIRED | 0 | SAFETY | Correction accepted by supervisor | 2025-11-10 10:55 | INSTALLATION | SAFETY | Y | NO | N/A | N/A
RIYADH | 2512000177 | STAND ALONE POWER SOURCE | 0 | SAFETY | Correction accepted by supervisor | 2025-11-10 10:55 | INSTALLATION | SAFETY | Y | NO | N/A | N/A
RIYADH | 2512000177 | SIGNBOAD AS PER STC SPECIFICATION (DEMINSIONS, CLARITY, …ETC)? | 0 | Installation | Correction accepted by supervisor | 2025-11-10 10:56 | Safety | SAFETY | Y | NO | N/A | N/A
RIYADH | 2512000177 | HAVE ALL STC SAFETY MEASUREMENTS BEEN FOLLOWED? | 0 | Installation | Correction accepted by supervisor | 2025-11-10 10:56 | Safety | SAFETY | Y | NO | N/A | N/A
RIYADH | 2512000177 | ALL REQUIRED WORKER UNIFORM AND SAFETY ITEMS ARE PRESENT? | 48 | Installation | Correction accepted by supervisor | 2025-11-10 10:56 | Safety | SAFETY | Y | NO | N/A | N/A
RIYADH | 2512000177 | MUNCIPALITY PERMIT IS AVIALABLE ON THE SIGNBOARD? | 48 | Installation | Correction accepted by supervisor | 2025-11-10 11:35 | Safety | CIVIL | Y | NO | N/A | N/A
RIYADH | 2512000177 | NUMBER OF SIGNBOARDS AVAILABLE IN THE SITE ARE SUFFICIENT? | 72 | Installation | Correction accepted by supervisor | 2025-11-10 11:36 | Safety | CIVIL | Y | NO | N/A | N/A
RIYADH | 2512000177 | CONTRACTOR’S SIGNBOARD COMPLIED WITH THE PROJECT AND CONTRACTOR NAME ? | 48 | Installation | Correction accepted by supervisor | 2025-11-10 11:36 | Safety | CIVIL | Y | NO | N/A | N/A
RIYADH | 2512000177 | CONTRACTOR DETAILS AVAILBLE ON THE SIGNBOARD (NAME, PHONE NUMBER, … ETC) | 48 | Installation | Correction accepted by supervisor | 2025-11-10 11:36 | Safety | CIVIL | Y | NO | N/A | N/A
RIYADH | 2512000177 | ALL DAMAGE TO PROPERTY (TILES, CURBS, WALLS, ASPHALT) HAS BEEN REPAIRED TO ORIGINAL STATE OR AS PER CUSTOMER REQUEST AT WORK COMPLETION ? | 72 | Installation | Correction accepted by supervisor | 2025-11-10 11:36 | CIVIL | CIVIL | Y | NO | N/A | N/A
RIYADH | 2512000177 | SIGNBOAD AS PER STC SPECIFICATION (DEMINSIONS, CLARITY, …ETC)? | 0 | Installation | Rejected deviation approved by supervisor | 2025-11-24 12:42 | Safety | SAFETY | N | NO | N/A | N/A
RIYADH | 2512000177 | HAVE ALL STC SAFETY MEASUREMENTS BEEN FOLLOWED? | 0 | Installation | Correction accepted by supervisor | 2025-11-24 12:42 | Safety | SAFETY | Y | NO | N/A | N/A
RIYADH | 2512000177 | ALL REQUIRED WORKER UNIFORM AND SAFETY ITEMS ARE PRESENT? | 48 | Installation | Correction accepted by supervisor | 2025-11-24 12:42 | Safety | SAFETY | Y | NO | N/A | N/A
RIYADH | 2512000177 | NUMBER OF SIGNBOARDS AVAILABLE IN THE SITE ARE SUFFICIENT? | 72 | Installation | Correction accepted by supervisor | 2025-11-24 12:47 | Safety | CIVIL | Y | NO | N/A | N/A
RIYADH | 2512000177 | NO DEBRIS IS REMAINING ON THE SITE? | 48 | Installation | Correction accepted by supervisor | 2025-11-24 12:47 | CIVIL | CIVIL | Y | NO | N/A | N/A
RIYADH | 2512000177 | SIGNBOAD AS PER STC SPECIFICATION (DEMINSIONS, CLARITY, …ETC)? | 0 | Installation | Correction accepted by supervisor | 2025-11-27 11:23 | Safety | SAFETY | Y | NO | N/A | N/A
RIYADH | 2512000177 | NUMBER OF SIGNBOARDS AVAILABLE IN THE SITE ARE SUFFICIENT? | 72 | Installation | Correction accepted by supervisor | 2025-11-27 11:29 | Safety | CIVIL | Y | NO | N/A | N/A
RIYADH | 2512000177 | IS THE TRENCH ROUTE STRAIGHT? | 72 | Trenching/bore | Correction accepted by supervisor | 2025-11-27 11:34 | CIVIL | CIVIL | Y | NO | N/A | N/A
RIYADH | 2512000177 | PEDESTRIAN PASSES PLACED EVERY 100M IN FRONT OF CUSTOMER HOUSES AS REQUIRED | 0 | SAFETY | Correction accepted by supervisor | 2025-11-30 11:01 | INSTALLATION | SAFETY | Y | NO | N/A | N/A
RIYADH | 2512000177 | HAVE ALL STC SAFETY MEASUREMENTS BEEN FOLLOWED? | 0 | Installation | Correction accepted by supervisor | 2025-11-30 11:01 | Safety | SAFETY | Y | NO | N/A | N/A
RIYADH | 2512000177 | SIGNBOAD AS PER STC SPECIFICATION (DEMINSIONS, CLARITY, …ETC)? | 0 | Installation | Correction accepted by supervisor | 2025-12-10 11:02 | Safety | SAFETY | Y | NO | N/A | N/A
RIYADH | 2512000177 | HAVE ALL STC SAFETY MEASUREMENTS BEEN FOLLOWED? | 0 | Installation | Correction accepted by supervisor | 2025-12-10 11:02 | Safety | SAFETY | Y | NO | N/A | N/A
RIYADH | 2512000178 | WORKER NOT HOLDING STC ID BADGE | 0 | WORKER | Rejected deviation approved by supervisor | 2025-11-27 07:03 | WORKER REGISTERATION | CIVIL | N | NO | Subcont. Related to Mohannad | Muhannad | Yes
RIYADH | 2512000178 | UNREGISTERED WORKER | 0 | WORKER | Rejected deviation approved by supervisor | 2025-11-27 07:03 | WORKER REGISTERATION | CIVIL | N | NO | Subcont. Related to Mohannad | Muhannad | Yes
RIYADH | 2512000178 | WORKER NOT HOLDING STC ID BADGE | 0 | WORKER | Rejected deviation approved by supervisor | 2025-11-27 07:03 | WORKER REGISTERATION | CIVIL | N | NO | Subcont. Related to Mohannad | Muhannad | Yes
RIYADH | 2512000178 | UNREGISTERED WORKER | 0 | WORKER | Rejected deviation approved by supervisor | 2025-11-27 07:03 | WORKER REGISTERATION | CIVIL | N | NO | Subcont. Related to Mohannad | Muhannad | Yes
RIYADH | 2512000178 | WORKER NOT HOLDING STC ID BADGE | 0 | WORKER | Rejected deviation approved by supervisor | 2025-11-27 07:04 | WORKER REGISTERATION | CIVIL | N | NO | Subcont. Related to Mohannad | Muhannad | Yes
RIYADH | 2512000178 | UNREGISTERED WORKER | 0 | WORKER | Rejected deviation approved by supervisor | 2025-11-27 07:04 | WORKER REGISTERATION | CIVIL | N | NO | Subcont. Related to Mohannad | Muhannad | Yes
RIYADH | 2512000178 | WORKER NOT HOLDING STC ID BADGE | 0 | WORKER | Rejected deviation approved by supervisor | 2025-11-27 07:04 | WORKER REGISTERATION | CIVIL | N | NO | Subcont. Related to Mohannad | Muhannad | Yes
RIYADH | 2512000178 | UNREGISTERED WORKER | 0 | WORKER | Rejected deviation approved by supervisor | 2025-11-27 07:05 | WORKER REGISTERATION | CIVIL | N | NO | Subcont. Related to Mohannad | Muhannad | Yes
RIYADH | 2512000178 | WORKER NOT HOLDING STC ID BADGE | 0 | WORKER | Rejected deviation approved by supervisor | 2025-11-27 07:06 | WORKER REGISTERATION | CIVIL | N | NO | Subcont. Related to Mohannad | Muhannad | Yes
RIYADH | 2512000178 | UNREGISTERED WORKER | 0 | WORKER | Rejected deviation approved by supervisor | 2025-11-27 07:06 | WORKER REGISTERATION | CIVIL | N | NO | Subcont. Related to Mohannad | Muhannad | Yes
RIYADH | 2512000178 | WORKER NOT HOLDING STC ID BADGE | 0 | WORKER | Rejected deviation approved by supervisor | 2025-11-27 07:06 | WORKER REGISTERATION | CIVIL | N | NO | Subcont. Related to Mohannad | Muhannad | Yes
RIYADH | 2512000178 | UNREGISTERED WORKER | 0 | WORKER | Rejected deviation approved by supervisor | 2025-11-27 07:06 | WORKER REGISTERATION | CIVIL | N | NO | Subcont. Related to Mohannad | Muhannad | Yes
RIYADH | 2512000178 | Are stc existing NW infrastructure drawings available on site and marked on the ground according to stc specifications (e.g. distance from wall)? | 0 | Pre-survey | Rejected deviation approved by supervisor | 2025-11-27 07:12 | Pre-survey | CIVIL | N | YES | Subcont. Related to Mohannad | Muhannad
RIYADH | 2512000178 | IS THE TRENCH ROUTE STRAIGHT? | 72 | Trenching/bore | Correction accepted by supervisor | 2025-11-27 07:31 | CIVIL | CIVIL | N | NO | Subcont. Related to Mohannad | Muhannad
RIYADH | 2512000178 | PEDESTRIAN PASSES PLACED EVERY 100M IN FRONT OF CUSTOMER HOUSES AS REQUIRED | 0 | SAFETY | Closed Deviation With Penalty Approved by HQPM | 2025-11-30 07:05 | INSTALLATION | SAFETY | N | NO | Subcont. Related to Mohannad | Muhannad | Yes
RIYADH | 2512000178 | STAND ALONE POWER SOURCE | 0 | SAFETY | Closed Deviation With Penalty Approved by HQPM | 2025-11-30 07:05 | INSTALLATION | SAFETY | N | NO | Subcont. Related to Mohannad | Muhannad | Yes
RIYADH | 2512000178 | HAVE ALL STC SAFETY MEASUREMENTS BEEN FOLLOWED? | 0 | Installation | Closed Deviation With Penalty Approved by HQPM | 2025-11-30 07:05 | Safety | SAFETY | N | NO | Subcont. Related to Mohannad | Muhannad | Yes
RIYADH | 2512000178 | NUMBER OF SIGNBOARDS AVAILABLE IN THE SITE ARE SUFFICIENT? | 72 | Installation | Closed Deviation With Penalty Approved by HQPM | 2025-11-30 07:19 | Safety | CIVIL | N | NO | Subcont. Related to Mohannad | Muhannad | Yes
RIYADH | 2512000178 | NO DEBRIS IS REMAINING ON THE SITE? | 48 | Installation | Closed Deviation With Penalty Approved by HQPM | 2025-11-30 07:19 | CIVIL | CIVIL | N | NO | Subcont. Related to Mohannad | Muhannad | Yes
RIYADH | 2512000178 | HAS THE TRENCH BEEN CLOSED WITHIN 24 HOURS OF OPENING? | 72 | Installation | Closed Deviation With Penalty Approved by HQPM | 2025-11-30 07:19 | Safety | CIVIL | N | NO | Subcont. Related to Mohannad | Muhannad | Yes
RIYADH | 2512000178 | IS THE TRENCH ROUTE STRAIGHT? | 72 | Trenching/bore | Closed Deviation With Penalty Approved by HQPM | 2025-11-30 07:19 | CIVIL | CIVIL | N | NO | Subcont. Related to Mohannad | Muhannad | Yes
RIYADH | 2512000178 | CONTRACTOR MARKED THE TRENCH PATH AS PER THE DESIGN BEFORE START TRENCHING ? | 0 | Trenching/bore | Closed Deviation With Penalty Approved by HQPM | 2025-11-30 07:19 | CIVIL | CIVIL | N | NO | Subcont. Related to Mohannad | Muhannad | Yes
RIYADH | 2512000178 | THE TRENCH WIDTH IS AS PER DESIGN SPECIFICATIONS AND MEETS STC REQUIREMENTS? | 72 | Trenching/bore | Closed Deviation With Penalty Approved by HQPM | 2025-11-30 07:19 | Standards | CIVIL | N | NO | Subcont. Related to Mohannad | Muhannad | Yes
RIYADH | 2512000178 | ALL REQUIRED WORKER UNIFORM AND SAFETY ITEMS ARE PRESENT? | 48 | Installation | Correction accepted by supervisor | 2025-11-30 07:47 | Safety | SAFETY | Y | NO | Subcont. Related to Mohannad | Muhannad
RIYADH | 2512000178 | WORKER NOT HOLDING STC ID BADGE | 0 | WORKER | Rejected deviation approved by supervisor | 2025-12-02 07:58 | WORKER REGISTERATION | CIVIL | N | NO | Subcont. Related to Mohannad | Muhannad | Yes
RIYADH | 2512000178 | UNREGISTERED WORKER | 0 | WORKER | Rejected deviation approved by supervisor | 2025-12-02 07:58 | WORKER REGISTERATION | CIVIL | N | NO | Subcont. Related to Mohannad | Muhannad | Yes
RIYADH | 2512000178 | WORKER NOT HOLDING STC ID BADGE | 0 | WORKER | Rejected deviation approved by supervisor | 2025-12-02 07:59 | WORKER REGISTERATION | CIVIL | N | NO | Subcont. Related to Mohannad | Muhannad | Yes
RIYADH | 2512000178 | UNREGISTERED WORKER | 0 | WORKER | Rejected deviation approved by supervisor | 2025-12-02 07:59 | WORKER REGISTERATION | CIVIL | N | NO | Subcont. Related to Mohannad | Muhannad | Yes
RIYADH | 2512000178 | WORKER NOT HOLDING STC ID BADGE | 0 | WORKER | Rejected deviation approved by supervisor | 2025-12-02 07:59 | WORKER REGISTERATION | CIVIL | N | NO | Subcont. Related to Mohannad | Muhannad | Yes
RIYADH | 2512000178 | UNREGISTERED WORKER | 0 | WORKER | Rejected deviation approved by supervisor | 2025-12-02 07:59 | WORKER REGISTERATION | CIVIL | N | NO | Subcont. Related to Mohannad | Muhannad | Yes
RIYADH | 2512000178 | IS THE TRENCH ROUTE STRAIGHT? | 72 | Trenching/bore | Rejected deviation approved by supervisor | 2025-12-02 08:17 | CIVIL | CIVIL | N | NO | Subcont. Related to Mohannad | Muhannad
RIYADH | 2512000178 | WORKER NOT HOLDING STC ID BADGE | 0 | WORKER | Rejected deviation approved by supervisor | 2025-12-03 07:39 | WORKER REGISTERATION | CIVIL | N | NO | Subcont. Related to Mohannad | Muhannad | Yes
RIYADH | 2512000178 | UNREGISTERED WORKER | 0 | WORKER | Rejected deviation approved by supervisor | 2025-12-03 07:39 | WORKER REGISTERATION | CIVIL | N | NO | Subcont. Related to Mohannad | Muhannad | Yes
RIYADH | 2512000178 | PEDESTRIAN PASSES PLACED EVERY 100M IN FRONT OF CUSTOMER HOUSES AS REQUIRED | 0 | SAFETY | Correction accepted by supervisor | 2025-12-03 07:44 | INSTALLATION | SAFETY | Y | NO | Subcont. Related to Mohannad | Muhannad
RIYADH | 2512000178 | ALL REQUIRED WORKER UNIFORM AND SAFETY ITEMS ARE PRESENT? | 48 | Installation | Correction accepted by supervisor | 2025-12-03 07:44 | Safety | SAFETY | N | NO | Subcont. Related to Mohannad | Muhannad
RIYADH | 2512000178 | IS THE TRENCH ROUTE STRAIGHT? | 72 | Trenching/bore | Correction accepted by supervisor | 2025-12-03 07:47 | CIVIL | CIVIL | Y | NO | Subcont. Related to Mohannad | Muhannad
RIYADH | 2512000178 | UNCERTIFIED WORKER | 0 | WORKER | Rejected deviation approved by supervisor | 2025-12-04 08:19 | WORKER REGISTERATION | CIVIL | N | NO | Subcont. Related to Mohannad | Muhannad | Yes
RIYADH | 2512000178 | UNCERTIFIED WORKER | 0 | WORKER | Rejected deviation approved by supervisor | 2025-12-04 08:19 | WORKER REGISTERATION | CIVIL | N | NO | Subcont. Related to Mohannad | Muhannad | Yes
RIYADH | 2512000178 | ALL REQUIRED WORKER UNIFORM AND SAFETY ITEMS ARE PRESENT? | 48 | Installation | Correction accepted by supervisor | 2025-12-04 08:22 | Safety | SAFETY | N | NO | Subcont. Related to Mohannad | Muhannad
RIYADH | 2512000178 | WORKER NOT HOLDING STC ID BADGE | 0 | WORKER | Rejected deviation approved by supervisor | 2025-12-07 08:13 | WORKER REGISTERATION | CIVIL | N | NO | Subcont. Related to Mohannad | Muhannad | Yes
RIYADH | 2512000178 | UNREGISTERED WORKER | 0 | WORKER | Rejected deviation approved by supervisor | 2025-12-07 08:13 | WORKER REGISTERATION | CIVIL | N | NO | Subcont. Related to Mohannad | Muhannad | Yes
RIYADH | 2512000178 | WORKER NOT HOLDING STC ID BADGE | 0 | WORKER | Rejected deviation approved by supervisor | 2025-12-07 08:14 | WORKER REGISTERATION | CIVIL | N | NO | Subcont. Related to Mohannad | Muhannad | Yes
RIYADH | 2512000178 | UNREGISTERED WORKER | 0 | WORKER | Rejected deviation approved by supervisor | 2025-12-07 08:14 | WORKER REGISTERATION | CIVIL | N | NO | Subcont. Related to Mohannad | Muhannad | Yes
RIYADH | 2512000178 | WORKER NOT HOLDING STC ID BADGE | 0 | WORKER | Rejected deviation approved by supervisor | 2025-12-07 08:15 | WORKER REGISTERATION | CIVIL | N | NO | Subcont. Related to Mohannad | Muhannad | Yes
RIYADH | 2512000178 | UNREGISTERED WORKER | 0 | WORKER | Rejected deviation approved by supervisor | 2025-12-07 08:15 | WORKER REGISTERATION | CIVIL | N | NO | Subcont. Related to Mohannad | Muhannad | Yes
RIYADH | 2512000178 | WORKER NOT HOLDING STC ID BADGE | 0 | WORKER | Rejected deviation approved by supervisor | 2025-12-07 08:15 | WORKER REGISTERATION | CIVIL | N | NO | Subcont. Related to Mohannad | Muhannad | Yes
RIYADH | 2512000178 | UNREGISTERED WORKER | 0 | WORKER | Rejected deviation approved by supervisor | 2025-12-07 08:15 | WORKER REGISTERATION | CIVIL | N | NO | Subcont. Related to Mohannad | Muhannad | Yes
RIYADH | 2512000178 | WORKER NOT HOLDING STC ID BADGE | 0 | WORKER | Rejected deviation approved by supervisor | 2025-12-07 08:16 | WORKER REGISTERATION | CIVIL | N | NO | Subcont. Related to Mohannad | Muhannad | Yes
RIYADH | 2512000178 | UNREGISTERED WORKER | 0 | WORKER | Rejected deviation approved by supervisor | 2025-12-07 08:16 | WORKER REGISTERATION | CIVIL | N | NO | Subcont. Related to Mohannad | Muhannad | Yes
RIYADH | 2512000178 | PEDESTRIAN PASSES PLACED EVERY 100M IN FRONT OF CUSTOMER HOUSES AS REQUIRED | 0 | SAFETY | Correction accepted by supervisor | 2025-12-07 08:26 | INSTALLATION | SAFETY | Y | NO | Subcont. Related to Mohannad | Muhannad
RIYADH | 2512000178 | HAVE ALL STC SAFETY MEASUREMENTS BEEN FOLLOWED? | 0 | Installation | Correction accepted by supervisor | 2025-12-07 08:26 | Safety | SAFETY | Y | NO | Subcont. Related to Mohannad | Muhannad
RIYADH | 2512000178 | ALL REQUIRED WORKER UNIFORM AND SAFETY ITEMS ARE PRESENT? | 48 | Installation | Correction accepted by supervisor | 2025-12-07 08:26 | Safety | SAFETY | N | NO | Subcont. Related to Mohannad | Muhannad
RIYADH | 2512000178 | NUMBER OF SIGNBOARDS AVAILABLE IN THE SITE ARE SUFFICIENT? | 72 | Installation | Correction accepted by supervisor | 2025-12-07 08:39 | Safety | CIVIL | Y | NO | Subcont. Related to Mohannad | Muhannad
RIYADH | 2512000178 | IS THE TRENCH ROUTE STRAIGHT? | 72 | Trenching/bore | Correction accepted by supervisor | 2025-12-07 08:39 | CIVIL | CIVIL | Y | NO | Subcont. Related to Mohannad | Muhannad
RIYADH | 2512000178 | PEDESTRIAN PASSES PLACED EVERY 100M IN FRONT OF CUSTOMER HOUSES AS REQUIRED | 0 | SAFETY | Correction accepted by supervisor | 2025-12-09 08:37 | INSTALLATION | SAFETY | Y | NO | Subcont. Related to Mohannad | Muhannad
RIYADH | 2512000178 | DID THE CONTRACTOR FIX ANY DAMAGED UTILITIES WITHIN 24 HOURS? | 24 | Trenching/bore | Correction accepted by supervisor | 2025-12-10 07:21 | CIVIL | CIVIL | N | NO | Subcont. Related to Mohannad | Muhannad
RIYADH | 2512000178 | NO DEBRIS IS REMAINING ON THE SITE? | 48 | Installation | Closed Deviation With Penalty Approved by HQPM | 2025-12-10 07:35 | CIVIL | CIVIL | N | NO | Subcont. Related to Mohannad | Muhannad | Yes
RIYADH | 2512000178 | HAVE ALL STC SAFETY MEASUREMENTS BEEN FOLLOWED? | 0 | Installation | Correction accepted by supervisor | 2025-12-10 07:36 | Safety | SAFETY | Y | NO | Subcont. Related to Mohannad | Muhannad
RIYADH | 2512000178 | PEDESTRIAN PASSES PLACED EVERY 100M IN FRONT OF CUSTOMER HOUSES AS REQUIRED | 0 | SAFETY | Correction accepted by supervisor | 2025-12-10 07:37 | INSTALLATION | SAFETY | Y | NO | Subcont. Related to Mohannad | Muhannad
RIYADH | 2512000178 | UNCERTIFIED WORKER | 0 | WORKER | Rejected deviation approved by supervisor | 2025-12-14 08:50 | WORKER REGISTERATION | CIVIL | N | NO | Subcont. Related to Mohannad | Muhannad | Yes
RIYADH | 2512000178 | UNCERTIFIED WORKER | 0 | WORKER | Rejected deviation approved by supervisor | 2025-12-14 08:50 | WORKER REGISTERATION | CIVIL | N | NO | Subcont. Related to Mohannad | Muhannad | Yes
RIYADH | 2512000178 | UNCERTIFIED WORKER | 0 | WORKER | Rejected deviation approved by supervisor | 2025-12-17 07:36 | WORKER REGISTERATION | CIVIL | N | NO | Subcont. Related to Mohannad | Muhannad | Yes
RIYADH | 2512000178 | MUNICIPALITY PERMITS ARE VALID AND RENEWED AS REQUIRED? | 0 | Trenching/bore | Closed Deviation With Penalty Approved by HQPM | 2025-12-17 07:41 | CIVIL | CIVIL | N | No | Subcont. Related to Mohannad | Muhannad | Yes
RIYADH | 2512000178 | WORKER NOT HOLDING STC ID BADGE | 0 | WORKER | Rejected deviation approved by supervisor | 2025-12-18 08:17 | WORKER REGISTERATION | CIVIL | N | NO | Subcont. Related to Mohannad | Muhannad | Yes
RIYADH | 2512000178 | WORKER NOT HOLDING STC ID BADGE | 0 | WORKER | Rejected deviation approved by supervisor | 2025-12-18 08:17 | WORKER REGISTERATION | CIVIL | N | NO | Subcont. Related to Mohannad | Muhannad | Yes
RIYADH | 2512000178 | UNREGISTERED WORKER | 0 | WORKER | Rejected deviation approved by supervisor | 2025-12-18 08:17 | WORKER REGISTERATION | CIVIL | N | NO | Subcont. Related to Mohannad | Muhannad | Yes
RIYADH | 2512000178 | UNREGISTERED WORKER | 0 | WORKER | Rejected deviation approved by supervisor | 2025-12-18 08:17 | WORKER REGISTERATION | CIVIL | N | NO | Subcont. Related to Mohannad | Muhannad | Yes
RIYADH | 2512000178 | WORKER NOT HOLDING STC ID BADGE | 0 | WORKER | Rejected deviation approved by supervisor | 2025-12-21 10:00 | WORKER REGISTERATION | CIVIL | N | NO | Subcont. Related to Mohannad | Muhannad | Yes
RIYADH | 2512000178 | UNREGISTERED WORKER | 0 | WORKER | Rejected deviation approved by supervisor | 2025-12-21 10:00 | WORKER REGISTERATION | CIVIL | N | NO | Subcont. Related to Mohannad | Muhannad | Yes
RIYADH | 2512000178 | WORKER NOT HOLDING STC ID BADGE | 0 | WORKER | Rejected deviation approved by supervisor | 2025-12-21 10:00 | WORKER REGISTERATION | CIVIL | N | NO | Subcont. Related to Mohannad | Muhannad | Yes
RIYADH | 2512000178 | WORKER NOT HOLDING STC ID BADGE | 0 | WORKER | Rejected deviation approved by supervisor | 2025-12-21 10:00 | WORKER REGISTERATION | CIVIL | N | NO | Subcont. Related to Mohannad | Muhannad | Yes
RIYADH | 2512000178 | UNREGISTERED WORKER | 0 | WORKER | Rejected deviation approved by supervisor | 2025-12-21 10:01 | WORKER REGISTERATION | CIVIL | N | NO | Subcont. Related to Mohannad | Muhannad | Yes
RIYADH | 2512000178 | UNREGISTERED WORKER | 0 | WORKER | Rejected deviation approved by supervisor | 2025-12-21 10:01 | WORKER REGISTERATION | CIVIL | N | NO | Subcont. Related to Mohannad | Muhannad | Yes
RIYADH | 2512000178 | WORKER NOT HOLDING STC ID BADGE | 0 | WORKER | Rejected deviation approved by supervisor | 2025-12-21 10:03 | WORKER REGISTERATION | CIVIL | N | NO | Subcont. Related to Mohannad | Muhannad | Yes
RIYADH | 2512000178 | UNREGISTERED WORKER | 0 | WORKER | Rejected deviation approved by supervisor | 2025-12-21 10:03 | WORKER REGISTERATION | CIVIL | N | NO | Subcont. Related to Mohannad | Muhannad | Yes
RIYADH | 2512000178 | NO DEBRIS IS REMAINING ON THE SITE? | 48 | Installation | Closed Deviation With Penalty Approved by HQPM | 2025-12-30 08:24 | CIVIL | CIVIL | N | NO | Subcont. Related to Mohannad | Muhannad | Yes
RIYADH | 2512000178 | ALL DAMAGE TO PROPERTY (TILES, CURBS, WALLS, ASPHALT) HAS BEEN REPAIRED TO ORIGINAL STATE OR AS PER CUSTOMER REQUEST AT WORK COMPLETION ? | 72 | Installation | Correction accepted by supervisor | 2025-12-31 08:26 | CIVIL | CIVIL | Y | NO | Subcont. Related to Mohannad | Muhannad
RIYADH | 2512000178 | ALL DAMAGE TO PROPERTY (TILES, CURBS, WALLS, ASPHALT) HAS BEEN REPAIRED TO ORIGINAL STATE OR AS PER CUSTOMER REQUEST AT WORK COMPLETION ? | 72 | Installation | Correction accepted by supervisor | 2026-01-14 12:26 | CIVIL | CIVIL | Y | NO | Subcont. Related to Mohannad | Muhannad
RIYADH | 2512000178 | ALL DAMAGE TO PROPERTY (TILES, CURBS, WALLS, ASPHALT) HAS BEEN REPAIRED TO ORIGINAL STATE OR AS PER CUSTOMER REQUEST AT WORK COMPLETION ? | 72 | Installation | Correction accepted by supervisor | 2026-01-18 08:20 | CIVIL | CIVIL | Y | NO | Subcont. Related to Mohannad | Muhannad
RIYADH | 2512000178 | NO DEBRIS IS REMAINING ON THE SITE? | 48 | Installation | Correction accepted by supervisor | 2026-01-19 10:00 | CIVIL | CIVIL | Y | NO | Subcont. Related to Mohannad | Muhannad
RIYADH | 2512000178 | ALL INSTALLED PROTECTIVE U-GUARDS MEET STC SPECIFICATIONS? | 72 | Installation | Correction accepted by supervisor | 2026-01-19 10:13 | Standards | Fiber | Y | NO | Subcont. Related to Mohannad | Muhannad
RIYADH | 2512000178 | ALL INSTALLED PROTECTIVE U-GUARDS MEET STC SPECIFICATIONS? | 72 | Installation | Correction accepted by supervisor | 2026-01-20 10:31 | Standards | Fiber | Y | NO | Subcont. Related to Mohannad | Muhannad
RIYADH | 2512000178 | ALL DAMAGE TO PROPERTY (TILES, CURBS, WALLS, ASPHALT) HAS BEEN REPAIRED TO ORIGINAL STATE OR AS PER CUSTOMER REQUEST AT WORK COMPLETION ? | 72 | Installation | Correction accepted by supervisor | 2026-01-26 07:27 | CIVIL | CIVIL | Y | NO | Subcont. Related to Mohannad | Muhannad
RIYADH | 2512000178 | ALL INSTALLED PROTECTIVE U-GUARDS MEET STC SPECIFICATIONS? | 72 | Installation | Correction accepted by supervisor | 2026-01-26 07:31 | Standards | Fiber | Y | NO | Subcont. Related to Mohannad | Muhannad
RIYADH | 2512000178 | NO DEBRIS IS REMAINING ON THE SITE? | 48 | Installation | Correction accepted by supervisor | 2026-01-28 12:36 | CIVIL | CIVIL | Y | NO | Subcont. Related to Mohannad | Muhannad
RIYADH | 2512000178 | ALL DAMAGE TO PROPERTY (TILES, CURBS, WALLS, ASPHALT) HAS BEEN REPAIRED TO ORIGINAL STATE OR AS PER CUSTOMER REQUEST AT WORK COMPLETION ? | 72 | Installation | Correction accepted by supervisor | 2026-01-29 07:54 | CIVIL | CIVIL | Y | NO | Subcont. Related to Mohannad | Muhannad
RIYADH | 2512000178 | ALL DAMAGE TO PROPERTY (TILES, CURBS, WALLS, ASPHALT) HAS BEEN REPAIRED TO ORIGINAL STATE OR AS PER CUSTOMER REQUEST AT WORK COMPLETION ? | 72 | Installation | Correction accepted by supervisor | 2026-02-04 07:30 | CIVIL | CIVIL | Y | NO | Subcont. Related to Mohannad | Muhannad
RIYADH | 2512000178 | ALL DAMAGE TO PROPERTY (TILES, CURBS, WALLS, ASPHALT) HAS BEEN REPAIRED TO ORIGINAL STATE OR AS PER CUSTOMER REQUEST AT WORK COMPLETION ? | 72 | Installation | Correction accepted by supervisor | 2026-02-09 10:10 | CIVIL | CIVIL | N | NO | Subcont. Related to Mohannad | Muhannad
RIYADH | 2512000178 | ALL INSTALLED PROTECTIVE U-GUARDS MEET STC SPECIFICATIONS? | 72 | Installation | Correction accepted by supervisor | 2026-02-12 09:25 | Standards | Fiber | N | NO | Subcont. Related to Mohannad | Muhannad
RIYADH | 2512000178 | ALL INSTALLED PROTECTIVE U-GUARDS MEET STC SPECIFICATIONS? | 72 | Installation | Correction accepted by supervisor | 2026-02-18 07:00 | Standards | Fiber | Y | NO | Subcont. Related to Mohannad | Muhannad
RIYADH | 2512000178 | ALL INSTALLED PROTECTIVE U-GUARDS MEET STC SPECIFICATIONS? | 72 | Installation | Correction accepted by supervisor | 2026-04-15 07:57 | Standards | Fiber | Y | NO | Subcont. Related to Mohannad | Muhannad
RIYADH | 2512000176 | WORKER NOT HOLDING STC ID BADGE | 0 | WORKER | Closed by HQ | 2025-11-04 09:07 | WORKER REGISTERATION | CIVIL | N | NO | N/A | N/A | Yes
RIYADH | 2512000176 | UNREGISTERED WORKER | 0 | WORKER | Closed by HQ | 2025-11-04 09:07 | WORKER REGISTERATION | CIVIL | N | NO | N/A | N/A | Yes
RIYADH | 2512000176 | PEDESTRIAN PASSES PLACED EVERY 100M IN FRONT OF CUSTOMER HOUSES AS REQUIRED | 0 | SAFETY | Correction accepted by supervisor | 2025-11-04 09:38 | INSTALLATION | SAFETY | Y | NO | N/A | N/A
RIYADH | 2512000176 | HAVE ALL STC SAFETY MEASUREMENTS BEEN FOLLOWED? | 0 | Installation | Correction accepted by supervisor | 2025-11-04 09:39 | Safety | SAFETY | Y | NO | N/A | N/A
RIYADH | 2512000176 | NUMBER OF SIGNBOARDS AVAILABLE IN THE SITE ARE SUFFICIENT? | 72 | Installation | Correction accepted by supervisor | 2025-11-04 10:05 | Safety | CIVIL | Y | NO | N/A | N/A
RIYADH | 2512000176 | ALL DAMAGE TO PROPERTY (TILES, CURBS, WALLS, ASPHALT) HAS BEEN REPAIRED TO ORIGINAL STATE OR AS PER CUSTOMER REQUEST AT WORK COMPLETION ? | 72 | Installation | Correction accepted by supervisor | 2025-11-04 10:05 | CIVIL | CIVIL | Y | NO | N/A | N/A
RIYADH | 2512000176 | SIGNBOAD AS PER STC SPECIFICATION (DEMINSIONS, CLARITY, …ETC)? | 0 | Installation | Correction accepted by supervisor | 2025-11-25 12:24 | Safety | SAFETY | Y | NO | N/A | N/A
RIYADH | 2512000176 | HAVE ALL STC SAFETY MEASUREMENTS BEEN FOLLOWED? | 0 | Installation | Correction accepted by supervisor | 2025-11-25 12:24 | Safety | SAFETY | Y | NO | N/A | N/A
RIYADH | 2512000176 | MUNICIPALITY PERMITS ARE VALID AND RENEWED AS REQUIRED? | 0 | Trenching/bore | Correction accepted by supervisor | 2025-11-25 12:35 | CIVIL | CIVIL | Y | No | N/A | N/A
RIYADH | 2512000176 | UNCERTIFIED WORKER | 0 | WORKER | Rejected deviation approved by supervisor | 2026-04-14 09:28 | WORKER REGISTERATION | CIVIL | N | NO | N/A | N/A | Yes
RIYADH | 2512000176 | UNCERTIFIED WORKER | 0 | WORKER | Rejected deviation approved by supervisor | 2026-04-14 09:28 | WORKER REGISTERATION | CIVIL | N | NO | N/A | N/A | Yes
RIYADH | 2512000176 | UNCERTIFIED WORKER | 0 | WORKER | Closed by HQ | 2026-04-19 10:15 | WORKER REGISTERATION | CIVIL | N | NO | N/A | N/A | Yes
RIYADH | 2512000176 | UNCERTIFIED WORKER | 0 | WORKER | Closed by HQ | 2026-04-28 09:25 | WORKER REGISTERATION | CIVIL | N | NO | N/A | N/A | Yes
RIYADH | 2512000176 | BADGE ID NOT CORRESPONDING TO WORKER | 0 | WORKER | Closed by HQ | 2026-04-28 10:06 | WORKER REGISTERATION | CIVIL | N | NO | N/A | N/A | Yes
RIYADH | 2512000176 | UNCERTIFIED WORKER | 0 | WORKER | Closed by HQ | 2026-04-29 07:53 | WORKER REGISTERATION | CIVIL | N | NO | N/A | N/A | Yes
RIYADH | 2512000176 | THE CONDUITS ARE INSTALLED PER STC SPECIFICATIONS? | 72 | Installation | Correction accepted by supervisor | 2026-04-30 11:39 | Ducts | CIVIL | N | NO | N/A | N/A
RIYADH | 2512000176 | THE INSTALLED HAND HOLE / MANHOLE INCLUDES ALL REQUIRED ACCESSORIES? | 72 | Material | Correction accepted by supervisor | 2026-04-30 11:48 | Hand hole/Manhole | CIVIL | N | NO | N/A | N/A
RIYADH | 2512000176 | UNCERTIFIED WORKER | 0 | WORKER | Rejected deviation approved by supervisor | 2026-05-02 09:14 | WORKER REGISTERATION | CIVIL | N | NO | N/A | N/A | Yes
RIYADH | 2512000176 | UNCERTIFIED WORKER | 0 | WORKER | Rejected deviation approved by supervisor | 2026-05-03 11:44 | WORKER REGISTERATION | CIVIL | N | NO | N/A | N/A | Yes

## Sheet1
WorkOrderNum | Total Deviation | Penalty applied | No penalty applied | Expected Penalty Waived | Civil Deviation | Civil Penalty applied | Fiber Deviation | Fiber Penalty applied | Safety Deviation | Safety Penalty applied | % OF Total | Civil Foreman | Inspector
2521001669 | 76 | 43 | 33 | 6 | 39 | 22 | 5 | 2 | 32 | 19 | 20.7% | Liyaqt | Mohamed Ali